## 공사일정_당일
id | date | location | task | person | details | tags | work_code | shift_type | category | source_kind | source_photo_upload_id | photo_plan_acknowledged | deleted_at | deleted_by | delete_reason | last_actor_user | last_actor_device | last_actor_at | created_at | is_deleted
307 | 2026-05-29 |  | 군포중 주변 지중화(총가) | 임재홍, 김종인, 최정우, 김기태, 김국진, 김성훈, 모범 1명, 김무선 | -저압 케이블 풀링 |  | TY25-004 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-28T09:34:59.573268 | 2026-05-28 18:34:59 | N
298 | 2026-05-29 |  | 광명 역세권 지구 저압 접속함 점검 | 이한열, 한동근, 변산 2명 |  |  | CG026-008 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-28T09:34:50.887563 | 2026-05-28 18:34:50 | N

## 공사일정_전체
id | date | location | task | person | details | tags | work_code | shift_type | category | source_kind | source_photo_upload_id | photo_plan_acknowledged | deleted_at | deleted_by | delete_reason | last_actor_user | last_actor_device | last_actor_at | created_at | is_deleted
60 | 2026-03-07 |  | 연화TR67 -> 접속, 진단, 송전(3구간) | [5 empty] | 일반 작업 | manual |  | 0 | 2026-03-31T06:41:38.920310 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-31T06:41:38.920310 | 2026-03-31 08:41:14 | Y
13 | 2026-03-25 | 미정 | 정우전설 대표님 미팅 | 정우전설 대표님 | 오후 4시 미팅 |  |  |  | 일반메모 | manual |  | 0 | 2026-03-26T06:18:57.235395 | admin |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-26T06:18:57.235395 | 2026-03-25 13:43:43 | Y
10 | 2026-03-26 | 연산동 | 플러그링크 굴착 | 미지정 |  | 야간 |  |  | 공사일정 | manual |  | 0 | 2026-03-26T08:12:06.963640 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-26T08:12:06.963640 | 2026-03-25 11:20:03 | Y
11 | 2026-03-26 | 샘모루 초교 | 케이블 포설 |  | 심야 작업 | 야간 |  |  | 공사일정 | manual |  | 0 | 2026-03-26T04:49:27.365175 | admin |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-26T04:49:27.365175 | 2026-03-25 11:21:15 | Y
12 | 2026-03-26 | 초평동 | 지중 전력 선로 가압 및 케이블 포설 입상 작업 | [5 empty] | 공사일정 | manual |  | 0 | 2026-03-26T08:13:16.228379 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-26T08:13:16.228379 | 2026-03-25 11:22:18 | Y
14 | 2026-03-26 |  |  | 전자칠판 |  |  |  |  | 공사일정 | manual |  | 0 | 2026-03-26T06:55:37.004306 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-26T06:55:37.004306 | 2026-03-26 13:24:41 | Y
15 | 2026-03-26 | 안양 | 야간작업 | - |  |  |  |  | 공사일정 | manual |  | 0 | 2026-03-26T04:48:01.523619 | admin |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-26T04:48:01.523619 | 2026-03-26 13:47:00 | Y
16 | 2026-03-26 | 군포 | 지중화 공사 | - |  |  |  |  | 공사일정 | manual |  | 0 | 2026-03-26T06:19:19.678838 | admin |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-26T06:19:19.678838 | 2026-03-26 13:51:34 | Y
18 | 2026-03-26 | 안양중 | 포설 공사 |  | 2026년 3월 26일부터 31일까지 진행되는 심야 포설 공사 일정입니다. | 심야 |  |  | 공사일정 | manual |  | 0 | 2026-03-26T08:13:12.687789 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-26T08:13:12.687789 | 2026-03-26 13:55:54 | Y
24 | 2026-03-26 | 안양 | NDLS 사진 촬영 | 임재홍, 김성훈 |  |  |  |  | 일반 작업 | manual |  | 0 |  |  |  | 조성현 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-27T06:44:11.371895 | 2026-03-27 11:44:18 | N
46 | 2026-03-26 | 안양 | 샘모루초교 케이블 포설(심야) | [5 empty] | 일반 작업 | manual |  | 0 | 2026-03-27T08:07:55.409664 | 조성현 | 현황판 인라인 삭제 | 조성현 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-27T08:07:55.410664 | 2026-03-27 17:07:50 | Y
47 | 2026-03-26 |  | 현장답사 | [5 empty] | 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-03-27T08:08:16.053987 | 2026-03-27 17:08:16 | N
23 | 2026-03-26 | 안양 | 샘모루초교 케이블 포설(심야) | 임재홍, 최정우, 김기태, 김국진, 김성훈, 김종인, 한동근 | 변산 2명, 모범 1명 |  |  |  | 공사 일정 | manual |  | 0 |  |  |  | 조성현 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-27T08:10:58.406795 | 2026-03-27 17:10:58 | N
17 | 2026-03-27 | 군포중 | 지중화 공사 추가작업 |  | 야간 추가작업 | 야간 |  |  | 공사일정 | manual |  | 0 | 2026-03-26T06:18:38.391495 | admin |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-26T06:18:38.392497 | 2026-03-26 13:55:04 | Y
19 | 2026-03-27 | 군포 | 지중화 공사 |  | 야간 지중화 공사 | 야간 |  |  | 공사일정 | manual |  | 0 | 2026-03-26T06:18:25.482488 | admin |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-26T06:18:25.482488 | 2026-03-26 14:15:41 | Y
20 | 2026-03-27 | 군포중 | 케이블 접속작업 | [5 empty] | 공사일정 | manual |  | 0 | 2026-03-26T08:57:40.618767 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-26T08:57:40.618767 | 2026-03-26 16:40:02 | Y
21 | 2026-03-27 | 샘모루초교 케이블 포설(심야) | 안양 비산동 | 전자칠판 | 김T |  |  |  | 공사일정 | manual |  | 0 | 2026-03-26T08:54:47.108767 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-26T08:54:47.108767 | 2026-03-26 17:16:10 | Y
28 | 2026-03-27 | 검증현장A | [검증] 공사일정 담당자공란 |  | auto-check | check |  |  | 공사일정 | manual |  | 0 | 2026-03-27T02:38:51.817674 | verify_user | 자동검증 정리 | verify_user | cursor-check | 2026-03-27T02:38:51.817674 | 2026-03-27 11:38:51 | Y
29 | 2026-03-27 |  | [검증] 일반작업 등록 | 전자칠판 | auto-check |  |  |  | 일반 작업 | manual |  | 0 | 2026-03-27T02:38:51.833674 | verify_user | 자동검증 정리 | verify_user | cursor-check | 2026-03-27T02:38:51.833674 | 2026-03-27 11:38:51 | Y
30 | 2026-03-27 | 검증현장A | [검증2] 공사일정 담당자공란 |  | auto-check | check |  |  | 공사일정 | manual |  | 0 | 2026-03-27T02:39:24.146060 | verify_user | 자동검증 정리 | verify_user | cursor-check | 2026-03-27T02:39:24.146060 | 2026-03-27 11:39:24 | Y
31 | 2026-03-27 |  | [검증2] 일반작업 등록 |  | auto-check |  |  |  | 일반 작업 | manual |  | 0 | 2026-03-27T02:39:24.166239 | verify_user | 자동검증 정리 | verify_user | cursor-check | 2026-03-27T02:39:24.166239 | 2026-03-27 11:39:24 | Y
32 | 2026-03-27 | 안양 비산 | 1 |  | 1 |  |  |  | 공사일정 | manual |  | 0 | 2026-03-27T02:46:56.123035 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-27T02:46:56.123035 | 2026-03-27 11:46:46 | Y
33 | 2026-03-27 |  | 저압 단가 | 임재홍, 이한열 |  |  |  |  | 일반 작업 | manual |  | 0 |  |  |  | 조성현 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-27T06:44:11.371895 | 2026-03-27 11:48:04 | N
34 | 2026-03-27 |  | 자재 여입 | 임재홍, 이한열 |  |  |  |  | 일반 작업 | manual |  | 0 |  |  |  | 조성현 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-27T06:44:11.371895 | 2026-03-27 11:48:09 | N
22 | 2026-03-27 | 안양 비산 | 샘모루초교 케이블 포설(심야) | 최정우, 김국진, 김성훈, 김종인, 한동근 | 변산2명, 모범 1명 |  |  |  | 공사 일정 | manual |  | 0 |  |  |  | 조성현 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-27T08:40:52.357411 | 2026-03-27 17:40:52 | N
44 | 2026-03-28 | 군포 | 지중화 공사 | [5 empty] | 공사일정 | manual |  | 0 | 2026-03-27T04:49:59.142008 | 상황판 | 현황판 인라인 삭제 | 상황판 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-27T04:49:59.142008 | 2026-03-27 13:43:55 | Y
48 | 2026-03-28 | 안양 | 샘모루초교 케이블 포설(심야) | [5 empty] | 일정 | manual |  | 0 | 2026-03-27T08:09:09.550705 | 조성현 | 현황판 인라인 삭제 | 조성현 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-27T08:09:09.550705 | 2026-03-27 17:09:05 | Y
49 | 2026-03-28 | 안양 | 샘모루초교 케이블 포설(심야) | [5 empty] | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-03-27T08:09:12.674713 | 2026-03-27 17:09:12 | N
50 | 2026-03-28 | 안양 | 돌발대기 | 이한열, 김기태 |  |  |  |  | 일정 | manual |  | 0 |  |  |  | 조성현 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-27T08:17:10.862150 | 2026-03-27 17:17:10 | N
26 | 2026-03-30 | 군포중 지중화 입상 케이블 포설 | 군포 | 전자칠판 | 이T, 최T, 김T, 김CJ, 김GI, 김GS, 모범 1명 |  |  |  | 공사일정 | manual |  | 0 | 2026-03-26T09:16:29.954371 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-26T09:16:29.954371 | 2026-03-26 18:15:18 | Y
35 | 2026-03-30 |  | 저압 단가 | 이한열, 한동근 | CO35 x 4L x 15mm 실리콘 접속제 |  |  |  | 일반 작업 | manual |  | 0 |  |  |  | 조성현 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-27T06:44:11.371895 | 2026-03-27 11:49:42 | N
25 | 2026-03-30 | 군포 | 군포중 지중화 입상 케이블 포설 | 임재홍, 최정우, 김국진, 김기태, 김성훈, 김종인, 김무선 | AL450x2개소, 접속원 투입 모범 1명 |  |  |  | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-31T06:57:49.566971 | 2026-03-31 15:57:49 | N
37 | 2026-03-31 |  | 광명 역세권지구 저압신규 1건(오후 2시 이후) | 임재홍, 한동근 |  |  |  |  | 일반 작업 | manual |  | 0 |  |  |  | 조성현 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-27T06:44:11.371895 | 2026-03-27 11:52:00 | N
77 | 2026-03-31 |  | 325 SQ 300m x 6 07:30 입고 (현대 건설 외상고장) 지게차 010-9141-9214 | [5 empty] | 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-03-31T06:46:46.857813 | 2026-03-31 15:46:46 | N
27 | 2026-03-31 | 군포 | 군포중 지중화 입상 케이블 포설 | 이한열, 최정우, 김국진, 김기태, 김성훈, 김종인, 김무선 | 모범 1명 |  |  |  | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-31T06:51:02.569397 | 2026-03-31 15:51:02 | N
36 | 2026-03-31 |  | 공동구 현장 조사 | 임재홍, 김도윤, 김상훈, 김무선 | 09:30 공동구 관리 사무소 |  |  |  | 일반 작업 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-31T06:51:21.430581 | 2026-03-31 15:51:21 | N
51 | 2026-04-01 | 안양 | 특별 회의 안전 교육 | [5 empty] | 일정 | manual |  | 0 | 2026-03-30T06:14:47.665357 | 조성현 | 현황판 인라인 삭제 | 조성현 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-30T06:14:47.665357 | 2026-03-27 17:18:47 | Y
53 | 2026-04-01 |  | 325 SQ 300m x 6 07:30 입고 (현대 건설 외상고장) 지게차 010-9141-9214 | [5 empty] | 일정 | manual |  | 0 | 2026-03-31T06:47:20.054199 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-31T06:47:20.054199 | 2026-03-27 17:31:40 | Y
39 | 2026-04-01 | 안산 | 안산 데이터 센터 방문 | 김무선, 김단후 |  |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-31T06:45:59.858925 | 2026-03-31 15:45:59 | N
78 | 2026-04-01 |  | TR 955a - 500m x 6D 07:30 입고 (호계동 533-1) |  | 지게차 02 -742- 1395 |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-31T06:49:27.765406 | 2026-03-31 15:49:27 | N
38 | 2026-04-01 |  | 안양 노후 케이블 교체 공사 | 임재홍, 최정우, 김국진, 한동근, 김상훈 | (연화 s/w 87 #1 ~ 연화 s/w 83 #3 1구간 약 26cm) 변산 2, 모범 2 |  | SY26-005 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-03T09:02:13.143413 | 2026-04-03 18:02:13 | N
52 | 2026-04-01 |  | 호계동 만안교통 신설 | 이한열, 김성훈, 김종인, 김기태, 이재규 | 관로(0,2,0) 역 28M(보도), TR 300KWA, 1대 T3-L 1조, 변산 3명, 모범 1명, 3W, 15t 덤프 |  | JY25-244 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-03T09:02:17.429663 | 2026-04-03 18:02:17 | N
57 | 2026-04-02 |  | 특별 회의 안전 교육(안양지사) 15:00~ | 이한열, 김국진, 김성훈, 김종인, 김무선, 김도윤, 김상훈, 이재규, 김단후 |  |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-03T05:36:31.662349 | 2026-04-03 14:36:31 | N
42 | 2026-04-02 |  | 광명 단가 기기 교체 | 임재홍, 김국진, 한동근, 김상훈 | 1. 광덕 TR7-P2 3상 300Kva -> 3상 300Kva -> 23시 ~ 01시 무정전 2. 소라TR 158-P4 3상 200Kva -> 3상 300Kva -> 01시 ~ 03시 -> 발전기 필요(신호등) 무정전 3. 소라 TR 161-P5 3상 75Kva -> 3상 75Kva -> 03시 ~ 05시 무정전 |  | SG25-004 | 심야 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-03T08:45:41.181414 | 2026-04-03 17:45:41 | N
41 | 2026-04-02 |  | 군포중 지중화 케이블 포설(AL40 x 1개소) | 김무선, 임재홍, 이한열, 최정우, 김종인, 김성훈, 김국진, 김기태, 한동근 |  |  | TY25-004 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-03T09:02:24.117486 | 2026-04-03 18:02:24 | N
43 | 2026-04-02 |  | 안양 케이블 교체 -> 접속, 진단, 송전 | 김상훈 |  |  | SY26-005 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-06T23:58:49.606354 | 2026-04-07 08:58:49 | N
82 | 2026-04-03 |  | 아침 7시 특고 케이블 AL95SQ * 600m * 3d 입고예정 | [5 empty] | 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-03-31T08:57:07.329030 | 2026-03-31 17:57:07 | N
56 | 2026-04-03 |  | 안양지사 착수회의 신촌 s/w 71 기간만료 오전 10시 | 김도윤 |  |  |  |  | 일정 | manual |  | 0 |  |  |  | 조성현 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-01T09:32:31.828248 | 2026-04-01 18:32:31 | N
94 | 2026-04-03 | 현장 사무실 | 회의 |  | 오후 4시 회의 진행 | 회의 |  |  | 일반메모 | manual |  | 0 | 2026-04-03T08:36:38.124464 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-03T08:36:38.124486 | 2026-04-03 15:03:00 | Y
40 | 2026-04-03 |  | 샘모루 초교 입상 케이블 포설 2개소 | 김국진, 최정우, 김성훈, 김기태, 김무선 | 영전사 접속 변산 2명, 모범 1명 |  | TY25-003 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-03T09:02:42.659201 | 2026-04-03 18:02:42 | N
88 | 2026-04-04 |  | 관로구방수장치 시공 (150파이 4개) | 김단후 | 임태욱소장 실행팀 진행 |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-03T09:02:36.132927 | 2026-04-03 18:02:36 | N
69 | 2026-04-06 |  | 김성훈 연차 | [5 empty] | 일정 | manual |  | 0 | 2026-04-06T01:18:56.131733 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-06T01:18:56.131756 | 2026-03-31 15:34:24 | Y
102 | 2026-04-06 |  | 단가 현장 답사 | 임재홍 | 개폐기 교체 준비 |  |  |  | 일정 | manual |  | 0 | 2026-04-05T23:42:14.088050 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-05T23:42:14.088072 | 2026-04-06 08:41:51 | Y
54 | 2026-04-06 |  | 연화 TR67 외 26년 경과 노후 변압기 선로 교체공사 | 임재홍, 최정우, 김국진, 김기태, 한동근, 김상훈 | -연화 s/w 40 #3 ~ 연화 s/w 44 #2 - CN 60 -> AL 95 약 250m (3구간) 변산 2명, 모범 2명 |  | SY26-005 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-07T07:21:50.311836 | 2026-04-07 16:21:50 | N
55 | 2026-04-06 |  | 호계동 만안 교통 접속 | 이재규 | 직선(75) 1조, 엘보(변60) 3조 오륜전기 |  | JY25-244 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-07T07:22:07.329704 | 2026-04-07 16:22:07 | N
72 | 2026-04-06 |  | 광명 역세권 기기 점검 예정 | 이한열, 김종인,김무선 | 변산 2명 |  | MY26-004 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:52:00.676704 | 2026-04-15 10:52:00 | N
65 | 2026-04-07 |  | 김성훈 연차 | [5 empty] | 일정 | manual |  | 0 | 2026-04-06T01:15:28.085995 | 상황판 | 현황판 인라인 삭제 | 상황판 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-06T01:15:28.086019 | 2026-03-31 15:31:51 | Y
84 | 2026-04-07 |  | 변압기 입고 07:30 TR150Kva 4eu |  | 지게차 010-5710-4725 광명단가 |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-02T00:07:39.921253 | 2026-04-02 09:07:39 | N
86 | 2026-04-07 |  | 만인 sw10 지상 개폐기 교체 공사 09:00 ~ 11:00 | [5 empty] | 공사 일정 | manual |  | 0 | 2026-04-02T23:44:29.763874 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-02T23:44:29.763893 | 2026-04-03 08:44:21 | Y
62 | 2026-04-07 |  | 군포중 지중화 직선 접속 | 김무선 |  |  | TY25-004 | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-03T08:50:31.629303 | 2026-04-03 17:50:31 | N
61 | 2026-04-07 |  | 연화TR67 -> 접속, 진단, 송전(3구간) | 김상훈 |  |  | SY26-005 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-03T09:02:53.766963 | 2026-04-03 18:02:53 | N
101 | 2026-04-07 |  | 초평동 한국토지주택공사 가로등(을) 1kw 신설(상용/임시)_3058 |  |  |  | JY26-019 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-03T09:02:57.852880 | 2026-04-03 18:02:57 | N
83 | 2026-04-07 |  | 광명, 안양 저압단가 | 최정우, 김국진, 이재규 |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 상황판 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-06T01:16:32.741641 | 2026-04-06 10:16:32 | N
114 | 2026-04-07 |  | 케이블 교체 준비 | 임재홍, 최정우, 김국진 |  |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-06T09:09:37.610842 | 2026-04-06 18:09:37 | N
58 | 2026-04-07 |  | 군포중 지중화 케이블포설(m/H~입상) | 김종인, 이한열, 김국진, 김기태, 김무선 | 변산 3명, 모범 1명 |  | TY25-004 | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-07T00:08:18.519953 | 2026-04-07 09:08:18 | N
85 | 2026-04-07 |  | 단가 현장 답사 | 임재홍 |  |  |  |  | 일정 | manual |  | 0 |  |  |  | 조성현 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-07T01:40:50.084286 | 2026-04-07 10:40:50 | N
100 | 2026-04-07 |  | 초평동599-25 한국토지주택공사 가로등(을) 2kw 신설(상용/임시)_3059 |  |  |  | JY26-018 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 조성현 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-07T01:41:01.694005 | 2026-04-07 10:41:01 | N
73 | 2026-04-07 |  | 광명 역세권 기기 점검 | 이한열, 김종인, 한동근, 김무선 |  |  | MY26-004 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:52:04.222690 | 2026-04-15 10:52:04 | N
74 | 2026-04-08 |  | 광명 역세권 기기 점검 예정 | [5 empty] | 일정 | manual |  | 0 | 2026-04-02T23:48:12.424350 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-02T23:48:12.424372 | 2026-03-31 15:40:46 | Y
80 | 2026-04-08 |  | 안양 샘모루 초교 케이블 포설 | 김성훈, 이한열, 김종인, 김국진, 김기태, 김무선 | 변산 2명, 모범 1명 |  | TY25-003 | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-03T08:50:59.253300 | 2026-04-03 17:50:59 | N
59 | 2026-04-08 |  | 군포중 지중화 케이블종단 입상 2개소 | 임재홍, 최정우, 김성훈, 한동근, 김무선 | 접속 - 영전사 |  | TY25-004 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-07T06:30:27.520972 | 2026-04-07 15:30:27 | N
63 | 2026-04-08 |  | 군포중 지중화 직선 접속 | 이재규 | 모범 1 접속(오륜전기) - 직선 |  | TY25-004 | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-08T00:59:06.796798 | 2026-04-08 09:59:06 | N
70 | 2026-04-09 |  | 초평동 지ㆍ전 선로가압, 종단 케이블 재4/신설 | 김무선 |  |  |  |  | 공사 일정 | manual |  | 0 | 2026-03-31T08:49:57.250673 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-03-31T08:49:57.250673 | 2026-03-31 15:38:18 | Y
75 | 2026-04-09 |  | 광명 역세권 기기 점검 예정 | [5 empty] | 일정 | manual |  | 0 | 2026-04-02T23:48:51.472322 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-02T23:48:51.472345 | 2026-03-31 15:40:54 | Y
66 | 2026-04-09 |  | 이한열 연차 | [5 empty] | 일정 | manual |  | 0 | 2026-04-06T01:52:03.732850 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-06T01:52:03.732873 | 2026-04-03 17:38:43 | Y
71 | 2026-04-09 |  | 안양 샘모루 초교 지중화 케이블 포설 | 김성훈, 김종인, 김국진, 김기태 | 변산 3명, 모범 1명 |  | TY25-003 | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-03T08:51:07.047373 | 2026-04-03 17:51:07 | N
110 | 2026-04-09 |  | 안양 샘모루 케이블 포설 mcm |  | 자재수령, 안양지사 325SQ 300 x 3 입고 |  |  |  | 일정 | manual |  | 0 | 2026-04-06T09:04:07.774698 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-06T09:04:07.774716 | 2026-04-06 18:03:51 | Y
112 | 2026-04-09 |  | 95SQ 500m x 6 07:30 입고 (안양단가) |  | 지게차 010-4492-9030 |  |  |  | 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-04-06T09:05:43.979825 | 2026-04-06 18:05:43 | N
111 | 2026-04-09 |  | 자재수령, 안양지사 325SQ 300m x 3 입고 | [5 empty] | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-06T09:05:53.372883 | 2026-04-06 18:05:53 | N
113 | 2026-04-09 |  | 대농 m/m2 : 4va 재설치, 현장조사(오후) | 임재홍, 최정우, 한동근 | 지게차 010-4492-9030 |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-06T09:07:40.189029 | 2026-04-06 18:07:40 | N
87 | 2026-04-09 |  | 만인 sw10 지상 개폐기 교체 공사 09:00 ~ 11:00 | 임재홍, 최정우, 한동근, 김도윤 | 대농 M/N2 : 4va 재설치, 현장조사(오후) |  | SY25-034 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 조성현 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-07T01:33:54.960450 | 2026-04-07 10:33:54 | N
64 | 2026-04-09 |  | 군포중 지중화 직선 접속 | 이재규 | 모범 1 |  | TY25-004 | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-07T07:20:48.704125 | 2026-04-07 16:20:48 | N
67 | 2026-04-10 |  | 군포중 지중화 직선 접속(야간) | [5 empty] | 공사 일정 | manual |  | 0 | 2026-04-02T23:56:01.115060 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-02T23:56:01.115083 | 2026-03-31 15:33:02 | Y
76 | 2026-04-10 |  | 광명 역세권 기기 점검 예정 | [5 empty] | 일정 | manual |  | 0 | 2026-04-02T23:48:55.090039 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-02T23:48:55.090060 | 2026-03-31 15:41:00 | Y
81 | 2026-04-10 |  | 안양 샘모루 초교 케이블 포설(야간) | [5 empty] | 공사 일정 | manual |  | 0 | 2026-04-02T23:56:04.189922 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-02T23:56:04.189944 | 2026-03-31 17:52:06 | Y
79 | 2026-04-10 |  | 초평동 지ㆍ전 선로가압, 입상 케이블 철거/재사, 26호 종단 케이블 철거 | 임재홍, 최정우, 이한열, 한동근, 김무선 | 3w : 오전 0.5 접속 - 영전사 변산 2명, 모범 1명 |  | TY25-005 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-07T06:31:21.438575 | 2026-04-07 15:31:21 | N
121 | 2026-04-10 |  | 광명 역세권 지구 기기점검(신호기) | 이한열, 김종인, 김기태, 한동근 |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-04-10T06:37:00.370655 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-10T06:37:00.370678 | 2026-04-08 09:32:40 | Y
134 | 2026-04-10 |  | 투개방 + 엘보분리 13:00 | 이재규 |  |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-09T23:34:52.899170 | 2026-04-10 08:34:52 | N
97 | 2026-04-13 |  | 비산동1111 한국환경공단 210kW 신설_3788 |  |  |  | JY25-248 | 주간 | 공사 일정 | manual |  | 0 | 2026-04-15T00:24:22.120758 | 김명호 | 현황판 인라인 삭제 | 김명호 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-15T00:24:22.120781 | 2026-04-03 18:04:12 | Y
98 | 2026-04-13 |  | 광명동 광명3동복합청사 고압 800KW 신설(광덕SW10-1) | 이한열, 김종인, 김기태, 한동근 |  |  | JG25-039 | 주간 | 공사 일정 | manual |  | 0 | 2026-04-15T00:24:07.757550 | 김명호 | 현황판 인라인 삭제 | 김명호 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-15T00:24:07.757573 | 2026-04-08 18:34:29 | Y
89 | 2026-04-13 |  | 연화 TR67외 26년 경과 노후 케이블 교체 공사 CE60 -> AL95 | 김상훈, 임재홍, 최정우, 김성훈, 김국진 | 연화 s/w 38 #1 ~ 연화 TR 67 HA -> 약 80m 변산 2명, 모범 1명 |  | SY26-005 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-12T23:51:59.982195 | 2026-04-13 08:51:59 | N
137 | 2026-04-13 |  | 광명 역세권 지구 기기점검(삼천리) | 이한열, 김종인, 김기태, 한동근 |  |  | MY26-004 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:52:33.562812 | 2026-04-15 10:52:33 | N
90 | 2026-04-14 |  | 부림 s/w 53 외 26년 경과 노후 케이블 교체 공사 | 김상훈 | 목련 s/w 33 #1 ~ 목련 s/w 45 #1 -> 약 220m |  | SY26-002 | 주간 | 공사 일정 | manual |  | 0 | 2026-04-15T00:24:51.405838 | 김명호 | 현황판 인라인 삭제 | 김명호 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-15T00:24:51.405860 | 2026-04-07 15:36:22 | Y
118 | 2026-04-14 |  | 케이블 접속, 진단, 송전 - 부림 s/w 33 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-04-07T07:19:45.918868 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-07T07:19:45.918890 | 2026-04-07 16:19:39 | Y
117 | 2026-04-14 |  | 케이블 접속, 진단, 송전 - 연화 s/w 42 | 김도윤 |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-04-15T01:38:02.583105 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:38:02.583129 | 2026-04-07 16:20:11 | Y
122 | 2026-04-14 |  | 안양 저압 단가 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-04-15T01:39:39.713639 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:39:39.713661 | 2026-04-08 09:33:19 | Y
91 | 2026-04-14 |  | 군포중 지중화 직선접속 |  | 모범1 |  | TY25-004 | 야간 | 공사 일정 | manual |  | 0 | 2026-04-15T01:38:55.687371 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:38:55.687392 | 2026-04-08 09:33:40 | Y
131 | 2026-04-14 |  | 2번 크레인 안전검사 14:00 (오룡) | 이한열, 한동근 |  |  |  |  | 일정 | manual |  | 0 | 2026-04-15T01:38:24.767655 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:38:24.767676 | 2026-04-10 08:37:09 | Y
138 | 2026-04-14 |  | 테스트 |  | 테스트중입니다 |  |  | 주간 | 일반 작업 | manual |  | 0 | 2026-04-15T01:37:48.633744 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:37:48.633765 | 2026-04-13 09:08:36 | Y
120 | 2026-04-14 |  | 평촌동 895 한국 환경 공단 신설 | 임재홍, 최정우, 김성훈, 김국진, 이재규 | - 도로 컷팅 : 40m x 2줄 |  | JY26-001 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:41:14.671116 | 2026-04-15 10:41:14 | N
146 | 2026-04-14 |  | 2번 크레인 안전검사 14:00 |  | -호룡사업소 |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:43:02.110461 | 2026-04-15 10:43:02 | N
147 | 2026-04-14 |  | 변압기 오일 펜스 설치 | [5 empty] | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:49:05.578351 | 2026-04-15 10:49:05 | N
148 | 2026-04-14 |  | 광명 삼천리 기기점검 | 이한열, 김종인, 김기태, 한동근, 김무선 | 개폐기 |  | MY26-004 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:51:53.609036 | 2026-04-15 10:51:53 | N
145 | 2026-04-14 |  | 대농 2 맨홀 저압 보수 | 최정우, 김성훈, 김국진, 김상훈 | - 4um 설치 및 점퍼선 설치 |  | SY25-011 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:52:51.317028 | 2026-04-15 10:52:51 | N
140 | 2026-04-14 |  | 안양 샘모루 지중화 | 김무선 | 고압접속 오륜전기 2명 |  | TY25-003 | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-16T09:20:17.010125 | 2026-04-16 18:20:17 | N
68 | 2026-04-15 |  | 82저 1112 크레인 안전검사 14:00 - 호룡수도권 사업소 | [5 empty] | 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-03-31T06:34:07.369994 | 2026-03-31 15:34:07 | N
96 | 2026-04-15 |  | 고천동227-4 고천프라자 350kW 신설_3762 |  |  |  | JY26-013 | 주간 | 공사 일정 | manual |  | 0 | 2026-04-15T01:34:48.163102 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:34:48.163125 | 2026-04-03 18:04:28 | Y
107 | 2026-04-15 |  | 부림 s/w 53 외 26년 경과 노후 케이블 교체 공사 |  | 목련 TR 33 HB ~ 신촌 s/w 16 #1 -> 약 186m |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-04-06T09:01:33.855563 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-06T09:01:33.855586 | 2026-04-06 18:01:24 | Y
106 | 2026-04-15 |  | 부림 s/w 53 외 26년 경과 노후 케이블 교체 공사 | 김상훈 | 부림 TR28 HB ~ 부림 s/w 72 #1 -> 약 95m |  | SY26-002 | 주간 | 공사 일정 | manual |  | 0 | 2026-04-15T00:28:11.795402 | 김명호 | 현황판 인라인 삭제 | 김명호 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-15T00:28:11.795423 | 2026-04-07 08:41:01 | Y
119 | 2026-04-15 |  | 케이블 접속, 진단, 송전 - 부림 s/w 33 | 김상훈 |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-04-15T01:33:32.801993 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:33:32.802017 | 2026-04-07 16:20:04 | Y
92 | 2026-04-15 |  | 군포중 지중화 직선접속 |  | 모범1 |  | TY25-004 | 야간 | 공사 일정 | manual |  | 0 | 2026-04-15T01:33:27.831066 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:33:27.831089 | 2026-04-08 09:34:19 | Y
116 | 2026-04-15 |  | 평촌동 895 한국 환경 공단 신설 | 이한열, 김성훈, 김종인, 김기태 | - 기초대 설치 : T-3L x 1조 - 관로굴착(도로 횡단) : 약 40m(0, 2, 0) |  | JY26-001 | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:36:18.379892 | 2026-04-15 10:36:18 | N
115 | 2026-04-15 |  | 비산동 1111 한국환경공단신설 | 임재홍, 최정우, 김성훈, 김종인, 김국진, 김기태, 이재규 | -관로 굴착(보도) : 20m (0, 0, 2) -보도 복구 : 1m x 20m -케이블 풀링(cv240x3, 120x1) : 약 25m -저압접속 : 동관 . BL |  | JY25-248 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:53:08.137179 | 2026-04-15 10:53:08 | N
132 | 2026-04-15 |  | 저압단가(초평동)-16개소 | 이한열, 한동근, 이재규 |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 Edg/146.0.0.0 | 2026-04-15T02:50:48.349909 | 2026-04-15 11:50:48 | N
93 | 2026-04-16 |  | 군포중 지중화 직선접속 |  |  |  | TY25-004 | 야간 | 공사 일정 | manual |  | 0 | 2026-04-15T01:37:27.665244 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:37:27.665265 | 2026-04-03 17:56:04 | Y
109 | 2026-04-16 |  | 안양 샘모루 케이블 포설 mcm |  |  |  |  | 야간 | 공사 일정 | manual |  | 0 | 2026-04-06T09:02:01.267485 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-06T09:02:01.267507 | 2026-04-06 18:01:53 | Y
108 | 2026-04-16 |  | 부림 s/w 53 외 26년 경과 노후 케이블 교체 공사 | 김상훈 | 목련 TR 33 HB ~ 신촌 s/w 16 #1 -> 약 186m |  | SY26-002 | 주간 | 공사 일정 | manual |  | 0 | 2026-04-15T01:29:43.129276 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:29:43.129298 | 2026-04-07 08:41:07 | Y
105 | 2026-04-16 |  | 안양 샘모루 케이블 포설 MCM |  |  |  | TY25-003 | 야간 | 공사 일정 | manual |  | 0 | 2026-04-09T23:33:06.584665 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-09T23:33:06.584686 | 2026-04-07 08:43:36 | Y
139 | 2026-04-16 |  | 야적장 점검(오전) | [5 empty] | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:37:02.964277 | 2026-04-15 10:37:02 | N
123 | 2026-04-16 |  | 연화 TR67 외 26년 경과 노후 케이블 교체 공사 | 임재홍, 최정우, 김국진, 한동근, 김상훈 | -구간: 연화 s/w 42 #1 ~ 연화 s/w96 #3(cn50 -> ca95) : 180m -접속(오륜전기) : 직선 95x1조, 데드 95x2조 변산 2명, 모범 2명, 오륜전기 2명 |  | SY26-005 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T23:50:28.612154 | 2026-04-16 08:50:28 | N
124 | 2026-04-16 |  | 평촌동 895 한국 환경 공단 신설 | 이한열, 김성훈, 김종인, 김기태, 이재규 | - 케이블 풀링(CA95) : 약 110m x 3D - 변압기 설치 : 31 300KVA x 1대 - 절체 및 케이블 절단 - 접속(오륜전기) : 직선95 x 2조, TR95 x 2조 모범 1명 |  | JY26-001 | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T23:54:03.830039 | 2026-04-16 08:54:03 | N
95 | 2026-04-17 |  | 관양동1020-1 현대드림모터스 89kw 증설_3040 |  |  |  | JY26-011 | 주간 | 공사 일정 | manual |  | 0 | 2026-04-15T01:46:12.909534 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:46:12.909556 | 2026-04-03 18:04:32 | Y
103 | 2026-04-17 |  | 최정우 연차 | [5 empty] | 일정 | manual |  | 0 | 2026-04-06T01:52:00.242533 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-06T01:52:00.242552 | 2026-04-06 08:54:00 | Y
129 | 2026-04-17 |  | 초평동599-25 한국토지주택공사 가로등(을) 2kw 신설(상용/임시)_3059 |  |  |  | JY26-018 | 주간 | 공사 일정 | manual |  | 0 | 2026-04-15T01:46:05.131628 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:46:05.131650 | 2026-04-08 11:35:16 | Y
130 | 2026-04-17 |  | 초평동 한국토지주택공사 가로등(을) 1kw 신설(상용/임시)_3058 |  |  |  | JY26-019 | 주간 | 공사 일정 | manual |  | 0 | 2026-04-15T01:46:00.921580 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:46:00.921603 | 2026-04-08 11:35:31 | Y
125 | 2026-04-17 |  | NDIS 사진 촬영 | 임재홍, 김국진, 한동근 |  |  |  |  | 일정 | manual |  | 0 | 2026-04-15T01:47:37.181297 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-15T01:47:37.181320 | 2026-04-08 18:38:07 | Y
133 | 2026-04-17 |  | 안양 샘모루 초교 케이블 포설 | 김성훈, 이한열, 김종인, 한동근 | 변산 3명, 모범 1명 |  | TY25-003 | 야간 | 공사 일정 | manual |  | 0 | 2026-04-16T07:53:32.228600 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-16T07:53:32.228623 | 2026-04-14 17:39:32 | Y
142 | 2026-04-17 |  | 광명 역세권 지구 기기점검(삼천리) |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-04-14T23:46:43.095623 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-14T23:46:43.095645 | 2026-04-15 08:46:26 | Y
149 | 2026-04-17 |  | 의왕 초평동 선로가압, 입상 케이블 철거/재사.종단 접속재 철거 | 임재홍, 김국진, 한동근 | 변산 3명, 모범 1명 |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-04-16T07:50:55.615207 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-16T07:50:55.615230 | 2026-04-15 10:47:09 | Y
141 | 2026-04-17 |  | 연화 TR67 외 26년 경과 노후 케이블 교체 공사 -> 절체지원 | 김상훈, 한동근 |  |  | SY26-005 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-16T07:51:34.928187 | 2026-04-16 16:51:34 | N
153 | 2026-04-17 |  | 비산동 샘모루 초교 주변 지중화(총가) | 김성훈, 이한열, 김종인, 한동근 | -고압케이블 풀링 -변산 3명 모범 1명 |  | TY25-003 | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-16T08:12:18.869466 | 2026-04-16 17:12:18 | N
152 | 2026-04-17 |  | 초평동 한국주택공사 지,전(총가) | 임재홍, 김국진, 한동근, 김무선 | -케이블 철거 및 입상 철거((A400):40m -관로 굴착 및 기설관로 연결 -케이블 철거 및 재사 포설 -입상금구류철거 *케이블 절단 -변산 3명, 모범 1명 |  | TY25-005 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-16T08:12:34.320328 | 2026-04-16 17:12:34 | N
154 | 2026-04-17 |  | 초평동 한국주택공사 지·전 (총가) | 임GS, 김GS, 한GS, 변전3명, 모바일1명, <김무성> | [팀] 공사1팀 케이블 철거 및 입상철거 (CA400): 40m, 관로 굴착 및 기설관로 연결 (311A x 1공), 케이블 철거 및 개소 도색 (CA400), 입상금구류 철거, *상추적 판별 케이블 절단 5톤 크레인, 1t, 1t 바가지 (실), 1번 카고, 5t 덤프, 3W-1대 (오후 05) |  |  |  | 공사 일정 | photo_plan |  | 1 | 2026-04-17T07:30:24.867942 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 Edg/146.0.0.0 | 2026-04-17T07:30:24.867963 | 2026-04-17 14:45:01 | Y
155 | 2026-04-17 |  | 비산동 샘모루 초교 주변 지중화 (총가) | 김TJ, 이TJ, 김CJ, 한GS, 변전3명, 모바일1명, <권우성> | [팀] 공사2팀 4/17 ~ 4/18 (야간) 고압케이블 풀링 5톤 크레인, 1번 크레인, 1t, 더블캡 |  |  | 야간 | 공사 일정 | photo_plan |  | 0 | 2026-04-17T07:30:37.729467 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 Edg/146.0.0.0 | 2026-04-17T07:30:37.729489 | 2026-04-17 14:45:01 | Y
156 | 2026-04-17 |  | 케이블 교체 복구 절체 지원 | 한GS, (김상훈) | [팀] 공사3팀 (주간) (09:00) 더블캡 |  |  | 주간 | 공사 일정 | photo_plan |  | 0 | 2026-04-17T07:30:33.775285 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 Edg/146.0.0.0 | 2026-04-17T07:30:33.775307 | 2026-04-17 14:45:01 | Y
157 | 2026-04-17 |  | 최정우 TJ 연차 | 최정우 TJ | [팀] 기타 (4/17, 4/20) |  |  |  | 공사 일정 | photo_plan |  | 0 | 2026-04-17T07:30:29.344495 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 Edg/146.0.0.0 | 2026-04-17T07:30:29.344516 | 2026-04-17 14:45:01 | Y
104 | 2026-04-20 |  | 최정우, 이한열 연차 | [5 empty] | 일정 | manual |  | 0 | 2026-04-06T01:52:11.403052 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-06T01:52:11.403075 | 2026-04-06 08:54:15 | Y
128 | 2026-04-20 |  | 비산동1111 한국환경공단 210kW 신설_3788 |  |  |  | JY25-248 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-04-08T02:34:38.012172 | 2026-04-08 11:34:38 | N
150 | 2026-04-20 |  | 투개방 09:30(엘보분기필요) | [5 empty] | 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-04-15T01:48:06.557531 | 2026-04-15 10:48:06 | N
158 | 2026-04-20 |  | 광명 삼천리 기기점검 | 김CJ, 한GS, 김우석 | [팀] 공사1팀 기기떼기 1t 바가지(주) |  |  |  | 공사 일정 | photo_plan |  | 0 | 2026-04-17T08:45:12.052763 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-17T08:45:12.052784 | 2026-04-17 17:45:06 | Y
160 | 2026-04-20 |  | 만안 TR 24리 노후케이블 교체 (SJE) | 김SJ, 김JS, 김GS, 김GS, 변전 2명, 보조 1명, 김상훈 | [팀] 공사2팀 구간: 삼성 5/12 #1 ~ 삼성 TR 2 #4B (CNCV -> CA98) = 약 30m. 접속(오렌지): TR 1차 x 1조, 테이프 8자 x 2 5톤 크레인, 더블캡 (김상훈) |  |  |  | 공사 일정 | photo_plan |  | 0 | 2026-04-17T08:45:35.893718 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-17T08:45:35.893740 | 2026-04-17 17:45:06 | Y
161 | 2026-04-20 |  | NDIS 사진 촬영 | 김JS, 김GS, 변전 1명 | [팀] 공사2팀 NDIS 사진 촬영 |  |  |  | 공사 일정 | photo_plan |  | 0 | 2026-04-17T08:45:56.629437 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-17T08:45:56.629459 | 2026-04-17 17:45:06 | Y
164 | 2026-04-20 |  | NDIS 사진 촬영 | 김TD, 김GS, 변전 1명, 김도윤 | [팀] 공사3팀 NDIS 사진 촬영 더블캡 |  |  |  | 공사 일정 | photo_plan |  | 0 | 2026-04-17T08:46:00.037893 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-17T08:46:00.037914 | 2026-04-17 17:45:06 | Y
165 | 2026-04-20 |  | 연차 (4/20) | 이한열 TS, 최정우 TS | [팀] 기타 이한열 TS, 최정우 TS 연차 (4/20) |  |  |  | 공사 일정 | photo_plan |  | 0 | 2026-04-17T08:45:47.633039 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-17T08:45:47.633059 | 2026-04-17 17:45:06 | Y
163 | 2026-04-20 |  | 호계동 1223 홍재성 저압 | 임재홍, 김국진, 변산 1명, 김도윤 | 인입선 접속 = BS x 4 더블캡 |  |  | 주간 | 공사 일정 | photo_plan |  | 1 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-17T08:46:59.592707 | 2026-04-17 17:46:59 | N
162 | 2026-04-20 |  | 백운 5/12 #2 개방 및 일보분리 | 김성훈, 김도윤 | [팀] 공사3팀 절연캡 시공 A상 1t |  |  | 주간 | 공사 일정 | photo_plan |  | 1 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-17T08:47:20.733137 | 2026-04-17 17:47:20 | N
159 | 2026-04-20 |  | 광명 일직동 528-1 (삼천리 26-103) 저압 신규 | 김종인, 한동근, 김무선 | 접속함 접속 1t 바가지(주) |  |  | 주간 | 공사 일정 | photo_plan |  | 1 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-17T08:47:58.078012 | 2026-04-17 17:47:58 | N
143 | 2026-04-20 |  | 광명 역세권 지구 기기점검(삼천리) | 김종인, 한동근, 김무선 | -개폐기 |  | MY26-004 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-19T23:39:41.929723 | 2026-04-20 08:39:41 | N
136 | 2026-04-20 |  | 만안 TR 24 외 26년 경과 노후변압기 선로 교체공사 | 임재홍,김성훈,김국진,김기태,변산2명,모범1명,김상훈 | 상성 s/w 12 # 1 -> 상성 TR2 HA |  | SY25-019 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-19T23:40:37.928430 | 2026-04-20 08:40:37 | N
144 | 2026-04-20 |  | 안양 NDIS 사진 촬영 | 김성훈,김기태,변산1명,김상훈 |  |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-19T23:41:00.834274 | 2026-04-20 08:41:00 | N
126 | 2026-04-21 |  | 고천동227-4 고천프라자 350kW 신설_3762 |  |  |  | JY26-013 | 주간 | 공사 일정 | manual |  | 0 | 2026-04-20T07:57:24.686539 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-20T07:57:24.686560 | 2026-04-08 11:34:13 | Y
127 | 2026-04-21 |  | 비산동1111 한국환경공단 210kW 신설_3788 |  |  |  | JY25-248 | 주간 | 공사 일정 | manual |  | 0 | 2026-04-08T02:34:33.222613 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Safari/537.36 | 2026-04-08T02:34:33.222636 | 2026-04-08 11:34:28 | Y
172 | 2026-04-21 |  | 안양 샘모루 초교 J/B 신설 (2개소) | 임재홍, 김성훈, 최정우, 김국진, 모범 1명 |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-04-20T07:57:46.295220 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-20T07:57:46.295242 | 2026-04-17 17:54:56 | Y
177 | 2026-04-21 |  | 케이블 입고 (07:00 창고) | - | [팀] 기타 CE 325 : 300m x 3D, 지게차 대여 : 010-8633-9325 |  |  |  | 공사 일정 | photo_plan |  | 0 | 2026-04-20T07:55:52.404924 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-20T07:55:52.404945 | 2026-04-20 16:52:45 | Y
174 | 2026-04-21 |  | 광명 삼천리 기기 점검 | 이한열, 김종인, 김기태, 한동근 | 개폐기 - 2팀 1t (바가지-구) |  |  | 주간 | 공사 일정 | photo_plan |  | 1 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-20T07:53:50.548023 | 2026-04-20 16:53:50 | N
173 | 2026-04-21 |  | 케이블 입고 07:00 입고 광명 단가 |  | CE325 : 300(m x 3D) 지게차 010-8633-9325 |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-20T07:55:47.802615 | 2026-04-20 16:55:47 | N
175 | 2026-04-21 |  | 공드럼 반출 (우성목재) |  | 고압드럼 |  |  |  | 일정 | photo_plan |  | 1 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-20T07:57:00.539379 | 2026-04-20 16:57:00 | N
176 | 2026-04-21 |  | 비산동 샘모루초교 주변지중화(총가) | 임재홍, 김성훈, 최정우, 김국진, 모범 1명 | 접속함설치, 관로굴착 더블캡, 미니크레인, 1t바가지, 5t덤프, 3w-1대 |  |  | 주간 | 공사 일정 | photo_plan |  | 1 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-20T07:57:35.953900 | 2026-04-20 16:57:35 | N
99 | 2026-04-22 |  | 광명동 광명3동복합청사 고압 800KW 신설(광덕SW10-1) |  |  |  | JG25-039 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) | 2026-04-03T09:04:38.393211 | 2026-04-03 18:04:38 | N
169 | 2026-04-22 |  | 안양 개폐기 점검 | 이한열, 김기태 |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-04-21T08:36:54.549435 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-21T08:36:54.549458 | 2026-04-17 17:51:56 | Y
178 | 2026-04-22 |  | 고천동227-4 고천프라자 350kW 신설_3762 |  |  |  | JY26-013 | 주간 | 공사 일정 | manual |  | 0 | 2026-04-20T07:58:18.884726 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-20T07:58:18.884747 | 2026-04-20 16:57:22 | Y
185 | 2026-04-22 |  | 비산동 샘모루초교 주변 지중화 (종가) | 권TJ, 김CJ, 최TJ, 김GJ, 한GS, 모범2명, 오륜전기(2명) | [팀] 공사2팀 접속함 설치, 관로굴착, 보도복구, 접속 (오륜전기) 2개소 3.5t 마이티, 1.2t 마이티, 더블캡, 2.5t 덤프, 3W - 1대 |  |  |  | 공사 일정 | photo_plan |  | 0 | 2026-04-21T08:37:24.253035 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-21T08:37:24.253059 | 2026-04-21 17:36:22 | Y
186 | 2026-04-22 |  | 자재 반입, 현장 조사, 자재 구매 | 최SJ, 견습 1명 | [팀] 공사3팀 자재 반입, 현장 조사, 자재 구매 1t 크레인, 1t 바가지 (구) |  |  |  | 공사 일정 | photo_plan |  | 0 | 2026-04-21T08:39:17.879009 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-21T08:39:17.879030 | 2026-04-21 17:36:22 | Y
187 | 2026-04-22 |  | 변압기 입고 (창고 이사) | - | [팀] 기타 3Φ 150kVA (N) x 2대 (지게차비: 010-8934-7501) |  |  |  | 공사 일정 | photo_plan |  | 0 | 2026-04-21T08:40:45.441734 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-21T08:40:45.441754 | 2026-04-21 17:36:22 | Y
184 | 2026-04-22 |  | 26년도 지상개폐기 점검 (안양지사) | 이한열, 김기태 | 안양지사 - 1건 1t |  |  | 주간 | 공사 일정 | photo_plan |  | 1 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-21T08:36:49.192099 | 2026-04-21 17:36:49 | N
151 | 2026-04-22 |  | 비산동 샘모루초교 주변 지중화 (총가) | 김성훈, 최정우, 김종인, 한동근, 모범 1명 |  |  | TY25-003 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-21T08:37:20.512988 | 2026-04-21 17:37:20 | N
135 | 2026-04-22 |  | 변압기 입고(창고 7시) |  | 3 150kva x 2대 지게차 : 010-8934-7501 |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-21T08:38:53.232613 | 2026-04-21 17:38:53 | N
188 | 2026-04-22 |  | 현장조사 | 임재홍 | 변산 1명 |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-21T08:40:03.046555 | 2026-04-21 17:40:03 | N
171 | 2026-04-22 |  | 자재여입 | 임재홍 | 변산 1명 |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-21T08:40:11.560902 | 2026-04-21 17:40:11 | N
189 | 2026-04-22 |  | 자재구매 | 임재홍 | 변산 1명 |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-21T08:40:19.346726 | 2026-04-21 17:40:19 | N
183 | 2026-04-23 |  | 안양 TR 동관단자 연결 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-04-21T04:20:19.599059 | 2026-04-21 13:20:19 | N
192 | 2026-04-23 |  | 고천동 227-4 고천프라자 장마W 신설 | 임SS, 최TJ, 김TJ, 김GJ, 한GS, 변산2명, 모법2명, <이재규> | [팀] 공사2팀 주간 도로컷팅: 20m x 2줄, 관로굴착: 약 3m (0.2, 0), 관로부설: (0.2, 0), 기초대 설치: T3-U x 1조 1번 크레인, 더블캡, 1번 미니 01, 5t 덤프, 6W-1대, 3W-1대, 15t 덤프-1대, 살수차 |  | JY26-013 | 주간 | 공사 일정 | photo_plan |  | 0 | 2026-04-22T08:46:00.116297 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-22T08:46:00.116320 | 2026-04-22 17:45:29 | Y
193 | 2026-04-23 |  | 비산동 샘모루초교 주변 지중화(총가) | 김TJ, 김CJ, 김GJ, 김GS, 변산3명, 모법1명, <김우석> | [팀] 공사3팀 4/23~4/24 (야간) 케이블 풀링 CA 400, 케이블 풀링 CA 95 1번 크레인, 3번 크레인, 1t, 더블캡 |  |  | 야간 | 공사 일정 | photo_plan |  | 0 | 2026-04-22T08:47:13.809560 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-22T08:47:13.809583 | 2026-04-22 17:45:29 | Y
168 | 2026-04-23 |  | 고천동 227-4 고천프라자 신설 | 임재홍, 최정우, 김성훈, 김기태, 변산 2명, 모벙 2명 | 관로(0,2,0) 약 40m, T-3U 1조, TR 500KVA(N-1) 1대 TR935Q |  | JY26-013 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-22T08:45:51.221154 | 2026-04-22 17:45:51 | N
190 | 2026-04-23 |  | 26년 지상개폐기 점검 (안양지사 - 2팀) | 이한열, 김종인, 김기태, 변산1명, 김무선 | 1t, 스카이(주) |  | JY26-037 | 주간 | 공사 일정 | photo_plan |  | 1 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-22T08:46:48.006919 | 2026-04-22 17:46:48 | N
166 | 2026-04-23 |  | 안양 샘모루 초교 케이블 포설 | 김성훈, 김종인, 김국진, 김기태, 변산 3명, 모범 1명 |  |  |  | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-23T08:17:53.294230 | 2026-04-23 17:17:53 | N
191 | 2026-04-23 |  | 광명 삼천리 기기 점검 | 이한열, 김종인, 김기태, 변산 1명 | [팀] 공사1팀 주간 개폐기 - 1개소 1t, 스카이(주) |  |  | 주간 | 공사 일정 | photo_plan |  | 1 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-23T08:38:27.174706 | 2026-04-23 17:38:27 | N
167 | 2026-04-24 |  | 케이블 포설, TR 설치 | 임재홍, 이한열, 최정우, 한동근, 모범 1명 |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-04-23T08:41:43.577728 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-23T08:41:43.577750 | 2026-04-17 17:49:56 | Y
200 | 2026-04-24 |  | 안양 샘모루 초교 케이블 포설 |  |  |  |  | 야간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-04-23T08:17:20.511340 | 2026-04-23 17:17:20 | N
201 | 2026-04-24 |  | 호계동 1003-7 저압 J/B 분리 (08:00) | 최정우, 이한열, 이재규 | [팀] 공사1팀 호계동 1003-7 저압 S/B 분리 (08:00) 더블캡 |  |  | 주간 | 공사 일정 | photo_plan |  | 1 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-23T08:39:15.417841 | 2026-04-23 17:39:15 | N
202 | 2026-04-24 |  | 고천동 207-4 교육청 64kW 신설 | 최정우, 이한열, 이재규 | [팀] 공사1팀 TR 수용가 압착 연결 CV 70 x 4L, TR 저압 압착 연결 - CV 70 x 4L 더블캡 |  |  | 주간 | 공사 일정 | photo_plan |  | 1 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-23T08:39:52.131427 | 2026-04-23 17:39:52 | N
203 | 2026-04-24 |  | 고천동 227-4 고천 프라자 350kW 신설 | 임재홍, 이한열, 최정우, 한동근, 모범1명, 이재규 | [팀] 공사2팀 케이블 철거 및 상부측 단말 절단, 케이블 풀링(CA95) = 100m x 3조, TR 설치 = 3Φ 500K x 1대, 접속(오전프라자) = 직선 95 x 2조, TR 95 x 2조 1t, 1번 크레인 |  | JY26-013 | 주간 | 공사 일정 | photo_plan |  | 1 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-23T08:40:49.001850 | 2026-04-23 17:40:48 | N
204 | 2026-04-24 |  | 오전동 32-7 오전 4구역 3250kW 신설 | 임재홍, 이한열, 최정우, 한동근 이재규 | [팀] 공사3팀 도로 컷팅 (현장조사) 2줄 (약 30m) 1번 매니더, 1t |  | 정수 | 주간 | 공사 일정 | photo_plan |  | 1 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-23T08:41:31.026592 | 2026-04-23 17:41:31 | N
170 | 2026-04-27 |  | 대농 m/h2 4UM 교체 |  |  |  |  | 야간 | 공사 일정 | manual |  | 0 | 2026-04-24T09:08:05.063422 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-24T09:08:05.063444 | 2026-04-17 17:52:22 | Y
180 | 2026-04-27 |  | 안양 샘모루초교 저압 입상, 전주신설 관로 구성 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-04-20T08:01:28.105068 | 2026-04-20 17:01:28 | N
182 | 2026-04-27 |  | 보상관련 지장물 조사 준비 | [5 empty] | 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-04-20T22:49:27.477886 | 2026-04-21 07:49:27 | N
205 | 2026-04-27 |  | 오전동 32-7 오전 나 구역 3,250k 신설 | 최정우, 김성훈, 김기태, 변산 4명, 모범 2명, 이재규 | 도로컷팅 관로굴착 기초대설치 |  | JY25-078 | 야간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-04-24T09:08:01.202402 | 2026-04-24 18:08:01 | N
206 | 2026-04-27 |  | 고천동 227-4 어반산업 115kw 신설 | 임재홍, 최정우, 김국진, 김기태, 변산 1명, 모범 1명, 이재규 |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-04-26T23:32:36.361735 | 2026-04-27 08:32:36 | N
211 | 2026-04-28 |  | 수암천 현장 집기류 전달 |  | 냉장고, 의자, 칠판 |  |  |  | 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-04-27T08:23:58.964705 | 2026-04-27 17:23:58 | N
199 | 2026-04-28 |  | 오전동 32-7 오전 나구역 3250kw | 최정우, 김성훈, 김국진, 변산 4명, 모범 2명, 이재규 |  |  | JY25-078 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-27T08:25:27.052736 | 2026-04-27 17:25:27 | N
209 | 2026-04-28 |  | 상동 580-1 의왕도시 공사 신설 | 임재홍, 최정우, 김성훈, 김기태, 변산 2명, 모범 1명, 이재규 | 기초대 설치 : 3W x 1조 관로 굴착 : 약 8m 케이블 재사 풀링 |  | JY25-147 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-27T08:25:37.778844 | 2026-04-27 17:25:37 | N
210 | 2026-04-28 |  | 26년 지상 개폐기 점검 | 이한열, 김종인, 김기태, 한동근, 김상훈 | 안양지사 |  | JY26-037 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-27T08:25:46.624087 | 2026-04-27 17:25:46 | N
198 | 2026-04-29 |  | 개폐기 점검 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-04-28T08:46:42.727405 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-28T08:46:42.727427 | 2026-04-23 17:15:54 | Y
197 | 2026-04-29 |  | 삼천리 수용가 엘보 접속 | 임재홍, 이한열 |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-04-28T08:46:38.566468 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-28T08:46:38.566491 | 2026-04-27 08:33:02 | Y
208 | 2026-04-29 |  | 1층 주차장 청소 및 정리, 공구 배치 | 임재홍, 한동근 |  |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-28T08:22:26.151916 | 2026-04-28 17:22:26 | N
207 | 2026-04-29 |  | 오전동 오전 나구역 접속 | 최정우, 이한열, 김국진, 변산 2명, 모범 1명, 이재규 | 케이블 풀링: CA400 x 약 120m x 3D 기기 설치, 접속(오륜전기) |  |  | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-28T08:44:18.395751 | 2026-04-28 17:44:18 | N
179 | 2026-04-29 |  | 초평동 한국 토지 공사 지장 전주 이설(총가) | 이한열, 김종인, 김기태, 변산 2명, 김무선 | 관로굴착, 접속함 설치, 저압풀링 및 접속, 저압 입상 |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-28T08:45:16.457122 | 2026-04-28 17:45:16 | N
212 | 2026-04-29 |  | 자재 수령 (정우자재) -15시 | 임재홍, 한동근 | 시흥 업체 수령 |  |  |  | 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-04-28T08:46:25.573051 | 2026-04-28 17:46:25 | N
196 | 2026-04-29 |  | 안양 샘모루 초교 맨홀 정리 | 김성훈, 김종인, 김기태, 모범1명 |  |  |  | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-28T08:47:17.630614 | 2026-04-28 17:47:17 | N
213 | 2026-04-29 |  | 안양 저압단가 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-04-28T08:48:10.157453 | 2026-04-28 17:48:10 | N
181 | 2026-04-30 |  | 대화감정 보상관련 지장물 조사 | [5 empty] | 일정 | manual |  | 0 |  |  |  | 김명호 | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-20T22:48:27.887560 | 2026-04-21 07:48:27 | N
195 | 2026-04-30 |  | 상동 의왕 도시 공사 | 임재홍, 최정우, 김성훈, 김국진, 변산 2, 모범 1,이재규 | -관로(0,2,0) 약 9m, TR95Sq 약 30m 1회선 신설 |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-29T05:09:34.588241 | 2026-04-29 14:09:34 | N
214 | 2026-04-30 |  | 삼천리 수용가 엘보 접속 | 임재홍, 한동근, 김무선 |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-04-29T05:10:05.339067 | 2026-04-29 14:10:05 | N
194 | 2026-04-30 |  | 안양 샘모루 초교 접속 | 오륜전기, 모범 1, 김무선 |  |  |  | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-29T05:10:27.666490 | 2026-04-29 14:10:27 | N
215 | 2026-05-02 |  | 수용가 엘보 재접속(오륜전기) | 이재규 | 범계 sw38 |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-29T05:11:08.850773 | 2026-04-29 14:11:08 | N
216 | 2026-05-04 |  | 안양초 지중화 민원 구간(맨홀) 도로커팅 | 김도윤 | 뚜껑 센터 기준 1.5m |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-30T05:31:30.273641 | 2026-04-30 14:31:30 | N
217 | 2026-05-04 |  | 저압단가 | 이재규 |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-30T05:31:37.056480 | 2026-04-30 14:31:37 | N
218 | 2026-05-04 |  | 개폐기 점검 | 김상훈 |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-04-30T05:31:45.374838 | 2026-04-30 14:31:45 | N
219 | 2026-05-06 |  | 비산동 샘모루 초교 주변 지중화(총가) | 임재홍, 이한열, 최정우, 김종인, 김성훈, 김국진, 김기태, 한동근 | 케이블 풀링(CA95) - 2구간 고압입상 : CA95x1조 (편출) 접속(영전사) : 종단95x1조 장주: 3개소(정장주) |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-05T23:40:50.042977 | 2026-05-06 08:40:50 | N
220 | 2026-05-07 |  | 삼양 변전소 PD 불량 직선 접속재 보수 | 임재홍, 오륜전기 |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-05-06T08:15:22.158221 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-06T08:15:22.158241 | 2026-04-30 14:26:18 | Y
222 | 2026-05-07 |  | 삼천리 수용가 엘보연결(오후) |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-05-06T08:15:10.822284 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-06T08:15:10.822306 | 2026-04-30 14:26:50 | Y
234 | 2026-05-07 |  | 군포로 JB 민원처리(보수) | 최정우, 한동근 |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-05T23:37:28.644851 | 2026-05-06 08:37:28 | N
236 | 2026-05-07 |  | 파영관 175 x 540m 07시 입고 | [5 empty] | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-05T23:38:23.662745 | 2026-05-06 08:38:23 | N
243 | 2026-05-07 |  | 부림 s/w5 외 수명 만료 노후 지중 케이블 교체 공사 | 김성훈, 김종인, 김기태, 김상훈 | 맨홀 양수 및 방수구 제거 사전 조사 야간 작업 준비 |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-06T08:12:13.675286 | 2026-05-06 17:12:13 | N
239 | 2026-05-07 |  | 저압 단가 2건 | 최정우, 한동근, 이재규 | 의왕 고천(Bssx4). 의왕학의<동관 35x4) |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-06T08:13:12.703866 | 2026-05-06 17:13:12 | N
235 | 2026-05-07 |  | 자재여입 | 이한열, 김국진 | 김GJ 오후 3시 <착공안전회의> 김상훈 => 안양지사 |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-06T08:14:15.220260 | 2026-05-06 17:14:15 | N
221 | 2026-05-07 |  | 안양초 지중화 | 최정우, 한동근, 이재규 | 맨홀 뚜껑 인상분 맨홀목 땜방 - 1개소 |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-06T08:14:57.630741 | 2026-05-06 17:14:57 | N
244 | 2026-05-07 |  | 접속제 바라시 | 이한열, 김국진 | 데드 60 x 2조, 데드 95 x 2조 TR 95 x 1조 |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-06T08:16:06.898172 | 2026-05-06 17:16:06 | N
245 | 2026-05-07 |  | 화성 남양 뉴타운 배전간선 | 임재홍, 오륜전기 2명, 김무선 | -남양 s/s 전력구 접속점 보수(오륜전기) VLF 진단 |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-06T08:28:24.954126 | 2026-05-06 17:28:24 | N
246 | 2026-05-07 |  | 일직동 511-2 전기공급(삼천리) | 임재홍, 오륜전기 2명, 김무선 | 삼천리 s/w 022H1-2 : 수용가 엘보연결 |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-06T08:29:17.081842 | 2026-05-06 17:29:17 | N
248 | 2026-05-07 |  | 군포중 주변 지중화 | 김성훈, 이한열, 김종인, 김국진, 김기태, 모범 1명, 김무선 | 케이블 풀링(CA400) |  |  | 야간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-06T08:30:36.361684 | 2026-05-06 17:30:36 | N
247 | 2026-05-07 |  | 비산동 샘모루 초교 주변 지중화 | 김성훈, 이한열, 김종인, 김국진, 김기태, 모범 1명, 김무선 | -케이블 풀링(CA400) |  |  | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-06T08:30:47.329438 | 2026-05-06 17:30:47 | N
223 | 2026-05-08 |  | 호계동 533-1 신설 |  | TR 325 SQ 약 280m 1회선 신설 |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-05-05T23:44:52.768461 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-05T23:44:52.768482 | 2026-04-30 14:27:43 | Y
225 | 2026-05-08 |  | 안양 샘모루 초교 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-05-05T23:44:45.376450 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-05T23:44:45.376471 | 2026-04-30 14:28:29 | Y
237 | 2026-05-08 |  | 고천동 현대산업개발(주) 임시 | 임재홍, 최정우, 한동근, 이재규 | -접속(영전사):데드 60x1조(시공 목표 : 560,000) |  | JY26-023 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-07T08:01:20.609000 | 2026-05-07 17:01:20 | N
238 | 2026-05-08 |  | 삼동580-1 의왕 도시공사 신설 접속 | 임재홍, 최정우, 한동근, 이재규 | -접속(영전사): 데드 50x1조, 데드95x2조 TR 95x1조(시공 목표 : 1.600,000) |  | JY25-147 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-07T08:02:39.946252 | 2026-05-07 17:02:39 | N
251 | 2026-05-08 |  | 고천동 227-4 어반산업 개발 신설 | 임재홍, 최정우, 한동근, 이재규 | -J/B 내 접속(BLx4 연결) |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-07T08:03:33.100782 | 2026-05-07 17:03:33 | N
252 | 2026-05-08 |  | 조작 안전회의 참석(안양지사 14:30) | 한동근, 김상훈 |  |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-07T08:04:14.745114 | 2026-05-07 17:04:14 | N
253 | 2026-05-08 |  | 케이블 입고(창고 07시) |  | CA400 : 400m x 3D (화물기사 : 010-8820-4960) 지게차비 : 010 - 9141 - 9214 |  |  |  | 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-07T08:05:06.730381 | 2026-05-07 17:05:06 | N
228 | 2026-05-11 |  | 안양 케이블 교체 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-05-08T08:48:03.255984 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-08T08:48:03.255984 | 2026-04-30 14:29:24 | Y
254 | 2026-05-11 |  | 고천동 현대 산업 임시 엘보변경 | 최정우, 김국진, 김도윤 | -수용가 엘보연결 (고텍 s/w 30 # 2) |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-08T08:45:43.470124 | 2026-05-08 17:45:43 | N
257 | 2026-05-11 |  | 고천동 227-4 어반산업 | 최정우, 김국진, 김도윤 | 시공 목표 : 500000 |  | JY26-021 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-08T08:46:32.316408 | 2026-05-08 17:46:32 | N
240 | 2026-05-11 |  | 부림 s/w5 외 수명 만료 노후 지중 케이블 교체 공사 | 임재홍, 최정우, 이한열, 김종인, 김국진, 김기태, 모범 1명, 김상훈 | 범계 s/w 73 #3 ~ 범계 s/w 95 #3 -> 약 300m 시공 목표 : 15,000,000 |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-08T08:46:50.209720 | 2026-05-08 17:46:50 | N
258 | 2026-05-11 |  | 산본 TR 41(영전사 미시공건) | 이한열, 한동근 | - 저압 연결(동관 50x 4 입착, 활선연결) - NDIS 사진 촬영 |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-08T08:47:57.459995 | 2026-05-08 17:47:57 | N
259 | 2026-05-11 |  | 현장 주말 돌발 대기(5/9 ~ 5/10) | 임재홍, 김국진 |  |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-11T08:14:09.537276 | 2026-05-11 17:14:09 | N
226 | 2026-05-12 |  | 삼성 s/w 20 돌발소산 지상개폐기 교체공사 | 김상훈 | 삼성 s/w 20 기기교체, 삼성 m/m 20 ~ 삼성 s/w 20 # 3 -> 약 40m |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-05-11T08:16:01.121781 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-11T08:16:01.121781 | 2026-05-06 08:49:23 | Y
229 | 2026-05-12 |  | 부림 s/w5 외 수명 만료 노후 지중 케이블 교체 공사 | 오륜전기 2명, 모범 1명, 김상훈 | -접속(오륜전기) -직선 95 x 1조, 데스95 x 2조 |  | SY26-016 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-11T08:13:54.079851 | 2026-05-11 17:13:54 | N
241 | 2026-05-12 |  | 비산 샘모루 초교 주변 지중화(총가) | 김성훈, 이한열, 김종인, 김국진, 김기태, 김무선 | 관로굴착(보도 통신 병행) - 2개소 - 보도 약 20m(0,1,0) - 보도 약 35m(0,0,1) 시공 목표 금액 : 3569920 |  |  | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-11T08:15:48.885790 | 2026-05-11 17:15:48 | N
262 | 2026-05-12 |  | 안양 접속함 주변 민원 처리 | 이재규 |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-11T08:19:16.553593 | 2026-05-11 17:19:16 | N
263 | 2026-05-12 |  | 우인찌 용접수리 | 임재홍, 김도윤 |  |  |  |  | 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-11T08:19:34.863039 | 2026-05-11 17:19:34 | N
264 | 2026-05-12 |  | 부곡동 가스 트론 신설 | 임재홍, 김도윤 | 수용가 엘보 연결 및 개폐기 투입 첨단 s/w 115 # 2 |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-11T08:20:13.721432 | 2026-05-11 17:20:13 | N
261 | 2026-05-12 |  | 내손 라구역 대우건설 160kw | 최정우, 이한열, 김성훈, 김종인, 김국진, 김기태, 한동근, 이재규 | 케이블 풀링(CA95): 약 40m x 3D (2라인) 변압기 설치 : 300kva(n1) x 1대 시공 목표 금액 : 3,000,000 |  | JY25-165 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-11T08:20:39.509982 | 2026-05-11 17:20:39 | N
260 | 2026-05-12 |  | 내손 라구역GS건설 300kw | 최정우, 이한열, 김성훈, 김종인, 김국진, 김기태, 한동근, 이재규 | -케이블 풀링(CA95) : 약 150m x 3D(2라인) 시공 목표 금액 : 8,400,000 |  | JY25-172 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-11T08:20:42.738995 | 2026-05-11 17:20:42 | N
230 | 2026-05-13 |  | 안양 케이블 교체 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-05-05T23:49:52.104654 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-05T23:49:52.104677 | 2026-04-30 14:29:39 | Y
233 | 2026-05-13 |  | 부림 s/w5 외 수명 만료 노후 지중 케이블 교체 공사 | 임재홍, 최정우, 한동근, 오륜전기 2명, 김상훈 | -구간: 부림 s/w 21 # 2 ~ 부림 s/w 22 # 3 : 7m(cn60 -> ca95) -접속(오륜전기) : 데드95 x 2조 -구간: 부림 s/w 29 # 4 ~ 부림 s/w 30 # 1 : 8m(cn60->ca95) -접속(오륜전기) : 데드95 x 2조 시공 목표 금액 : 2,350,000 |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-12T23:42:41.396063 | 2026-05-13 08:42:41 | N
227 | 2026-05-13 |  | 군포중 지중화(접속) | 오륜전기 2명, 모범 1명, 김무선 | -고압접속(오륜전기) -직선 x 4조 시공 목표 금액 : 3,550,000 |  |  | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-12T23:43:08.070695 | 2026-05-13 08:43:08 | N
250 | 2026-05-14 |  | NDIS 사진 촬영 2건 + 현장조사 | 임재홍, 이한열, 최정우, 김성훈, 김종인, 한동근 |  |  |  |  | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-07T23:42:10.426164 | 2026-05-08 08:42:10 | N
242 | 2026-05-14 |  | 군포중 지중화(접속) | 오륜전기 2명, 모범 1명, 김무선 | -접속(오륜전기) |  |  | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-13T08:14:03.358016 | 2026-05-13 17:14:03 | N
265 | 2026-05-14 |  | 케이블 입고(07시 창고) |  | 내손 라구역 GS건설 신설 CA95 : 500m x 6드럼 지게차 : 010 - 4492 - 9030 |  |  |  | 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-13T08:14:49.014581 | 2026-05-13 17:14:49 | N
231 | 2026-05-14 |  | 호계동 533-1 평촌 이반벨리 신설 | 최정우, 이한열, 김성훈, 김종인, 김국진, 한동근, 모범 2명, 이재규 | TR 325sq 약 280m 1회선 신설 |  | JY25-256 | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-13T08:15:16.089932 | 2026-05-13 17:15:16 | N
232 | 2026-05-15 |  | 안양 케이블 교체 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-04-30T05:29:52.086685 | 2026-04-30 14:29:52 | N
255 | 2026-05-15 |  | 26년 개폐기 점검 14시 | 임재홍, 김기태 |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-13T23:37:38.452374 | 2026-05-14 08:37:38 | N
267 | 2026-05-15 |  | 내손 라구역 주택동 150k 잠정 | 임재홍, 김기태 | 케이블 철거 : CA95 x 약 20m x 3D 입상 금구류 철거 |  | JY25-188 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-14T08:11:03.813994 | 2026-05-14 17:11:03 | N
266 | 2026-05-15 |  | 호계동 533-1 평촌 어반 관로굴착 09:00 | 임재홍, 김기태 | -관로굴착 : 약 20m(0,1,0) s/w~입상 가공 전주 활입 장비 지원 요청 |  | JY25-256 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-14T08:11:26.038192 | 2026-05-14 17:11:26 | N
249 | 2026-05-18 |  | 호계동 533-1 평촌 어반 밸리 신설 | 이한열, 최정우, 한동근, 이재규 | -케이블 풀링 : CA95 x 17M x 3D -고압 입상 : CA95 x 1조 -접속(영전사) : 데드 95 x 1조 신설 s/w #3 연결 |  | JY25-256 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-15T09:21:08.199450 | 2026-05-15 18:21:08 | N
268 | 2026-05-18 |  | CA95 x 500m -> 3등분 드럼감기 | 임재홍, 김성훈, 김종인, 김국진, 김기태 |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-15T09:21:56.278045 | 2026-05-15 18:21:56 | N
269 | 2026-05-18 |  | CE325x429m -> 2등분 드럼감기 | 임재홍, 김성훈, 김종인, 김국진, 김기태 |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-15T09:22:17.952045 | 2026-05-15 18:22:17 | N
270 | 2026-05-18 |  | 야적장 파렛트 반출처리 | 임재홍, 김성훈, 김종인, 김국진, 김기태 | -화성 양감면 업체 전달 |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-15T09:22:35.476285 | 2026-05-15 18:22:35 | N
271 | 2026-05-18 |  | 절연캡(개폐기) 세척 | [5 empty] | 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-15T09:22:47.850052 | 2026-05-15 18:22:47 | N
272 | 2026-05-18 |  | 삼동 580-1 의왕 도시공사 신설 | 김성훈, 김상훈 | -복구절체(오전 10:00) -수용가 엘보 연결 |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-15T09:23:26.273831 | 2026-05-15 18:23:26 | N
224 | 2026-05-19 |  | 안양동 682-3 현대건설 지중외상 고장 복구 공사(굴착) |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-04-30T05:28:08.825204 | 2026-04-30 14:28:08 | N
273 | 2026-05-19 |  | 안양 저압 단가 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-17T23:43:33.239037 | 2026-05-18 08:43:33 | N
274 | 2026-05-19 |  | 군포중 지중화 직선접속 |  |  |  |  | 야간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-17T23:43:46.552135 | 2026-05-18 08:43:46 | N
256 | 2026-05-20 |  | CE325SQx3Dx약 180m 케이블 철거 신설 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-05-19T09:03:15.105816 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-19T09:03:15.105816 | 2026-05-08 08:41:28 | Y
275 | 2026-05-20 |  | 광명역 역세권 지구 저압 접속함 점검 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-05-19T09:03:12.733339 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-19T09:03:12.733339 | 2026-05-18 08:44:05 | Y
286 | 2026-05-20 |  | 우천예정 정비 | 임재홍, 이한열, 김성훈, 김종인, 김국진, 김기태, 한동근 | -개폐기 절연캡 세척 -엔진오일 교환 -구조삼각대 및 산소통 교육 -그외 장비 정비 |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-19T09:04:05.032220 | 2026-05-19 18:04:05 | N
287 | 2026-05-20 |  | 신규 공사건 현장 협의 | 임재홍, 이재규 |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-19T09:04:16.889448 | 2026-05-19 18:04:16 | N
276 | 2026-05-21 |  | 26년 상반기 훈련 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-05-20T08:06:52.929375 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-20T08:06:52.929375 | 2026-05-18 08:44:32 | Y
277 | 2026-05-21 |  | 노후케이블 교체 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-05-20T08:06:51.105280 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-20T08:06:51.105280 | 2026-05-18 08:45:21 | Y
278 | 2026-05-21 |  | 안양동 682-3 현대건설 지중외상 복구공사 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-05-20T08:06:48.345374 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-20T08:06:48.345374 | 2026-05-18 08:45:37 | Y
279 | 2026-05-21 |  | 군포중 지중화 직선접속 | 오륜전기 2명, 모범 1명, 김무선 |  |  |  | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-20T08:06:26.583149 | 2026-05-20 17:06:26 | N
289 | 2026-05-21 |  | 고,저압 드럼 정리 | 최정우, 김기태, 한동근 |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-20T08:07:09.801736 | 2026-05-20 17:07:09 | N
290 | 2026-05-21 |  | 삼천리 접속함 점검 및 신용인 s/s 회의 | 임재홍, 김종인, 김무선 |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-20T08:07:42.810252 | 2026-05-20 17:07:42 | N
288 | 2026-05-21 |  | 자재수령 | 이한열, 김성훈, 김국진 |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-20T08:07:54.920225 | 2026-05-20 17:07:54 | N
291 | 2026-05-21 |  | 개폐기 인계 및 인수(안산 장상동) | 김종인, 김기태 | -44da |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-20T08:08:26.791778 | 2026-05-20 17:08:26 | N
292 | 2026-05-21 |  | 밀폐공간 구로 삼각대 안전교육 및 시연회 | 김성훈, 이한열, 김종인, 김국진, 김기태 |  |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-20T08:08:54.998877 | 2026-05-20 17:08:54 | N
293 | 2026-05-21 |  | 하얀지구 h314 노후케이블 교체 |  | -맨홀 양수 및 방수구 철거 - 3개소 -맨홀 뚜껑 땅에 묻힘 찾아야함 |  | SG026-007 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-20T08:09:40.421980 | 2026-05-20 17:09:40 | N
280 | 2026-05-22 |  | 하얀지구 노후 케이블 교체 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-05-21T07:54:45.992214 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-21T07:54:45.992214 | 2026-05-18 08:46:03 | Y
294 | 2026-05-22 |  | 학의동 1181 리젠시빌 신설 | 임재홍, 최정우, 이한열, 김성훈, 김국진, 김기태, 변산 1명, 이재규 | -기초대 설치 : 3w x 1조 -관로 굴착 : 약 3개(3, 0, 0) -케이블 풀링(CA95) -기기설치 |  | JY026-45 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-21T07:56:10.558685 | 2026-05-21 16:56:10 | N
281 | 2026-05-22 |  | 광명 역세권 지구 저압접속함 점검 | 김종인, 한동근, 변산 2명, 김무선 |  |  | CG026-008 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-27T08:37:57.381923 | 2026-05-27 17:37:57 | N
282 | 2026-05-26 |  | 광명 하안지구 H314 노후 케이블 교체 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-05-22T04:30:22.489296 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-22T04:30:22.489296 | 2026-05-19 09:29:27 | Y
285 | 2026-05-26 |  | 군포중 직선접속 |  |  |  |  | 야간 | 공사 일정 | manual |  | 0 | 2026-05-25T23:35:28.828727 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-25T23:35:28.828727 | 2026-05-19 09:30:47 | Y
295 | 2026-05-26 |  | 26년 특정 재원 지상 개폐기 교체 | 임재홍, 최정우, 김성훈, 김국진 | 소하 s/w 156 소하 s/w 90 |  | SG26-005 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-25T23:34:53.705618 | 2026-05-26 08:34:53 | N
284 | 2026-05-26 |  | 광명 역세권 접속함 점검(삼천리) | 이한열, 김종인, 김기태, 한동근 |  |  | CG026-008 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-27T08:36:09.951390 | 2026-05-27 17:36:09 | N
301 | 2026-05-27 |  | 광명동 광명시장 일반동 신설 | 최정우, 김성훈, 한동근, 모범 1명, 이재규 | - 기초대 설치 : 3w x 1조 - 관로굴착 - 시공 목표금액 : 4,007,000 |  | JG026-028 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-26T08:50:22.394415 | 2026-05-26 17:50:22 | N
302 | 2026-05-27 |  | NDIS 사진 촬영 | 임재홍, 이한열, 김국진 | 완료 후 접속함 점검 합류 |  |  | 주간 | 공사 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-26T08:50:48.003444 | 2026-05-26 17:50:48 | N
304 | 2026-05-27 |  | 케이블 입고(07시 창고) | 이한열 | ca95: 500m x 3D |  |  |  | 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-26T08:51:34.755290 | 2026-05-26 17:51:34 | N
305 | 2026-05-27 |  | 만안 s/w 40, 삼덕 M/u 외상고장 | 김종인 |  |  |  |  | 일정 | manual |  | 0 |  |  |  | 전자칠판 | lg-create-board | 2026-05-26T08:51:58.811177 | 2026-05-26 17:51:58 | N
306 | 2026-05-27 |  | 광명동 광명시장 일반용신설 | 최정우, 김성훈, 한동근, 변산 3명, 모범 2명, 이재규 | 관로굴착 기기설치 시공 목표 금액 : 4,500,000 |  | JG026-028 | 야간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-26T08:53:15.464707 | 2026-05-26 17:53:15 | N
296 | 2026-05-27 |  | 광명 역세권 지구 저압 접속함 점검 | 김종인, 김기태, 김무선 |  |  | CG026-008 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-27T08:36:05.487174 | 2026-05-27 17:36:05 | N
303 | 2026-05-27 |  | 군포중 주변 지중화 | 오륜전기 2명, 김무선 | 개폐기 접속 |  | TY25-004 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-27T08:37:38.898302 | 2026-05-27 17:37:38 | N
300 | 2026-05-28 |  | 호계동 평촌 어반밸리 수용가 가압 |  |  |  |  | 주간 | 공사 일정 | manual |  | 0 | 2026-05-27T08:37:31.151389 | admin | 현황판 인라인 삭제 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-27T08:37:31.151389 | 2026-05-22 13:31:25 | Y
297 | 2026-05-28 |  | 광명 역세권 지구 저압 접속함 점검 | 이한열, 김국진 |  |  | CG026-008 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-27T08:35:59.009406 | 2026-05-27 17:35:59 | N
299 | 2026-05-28 |  | 군포중 주변 지중화 | 임재홍, 김종인, 김기태, 변산 3명, 모범 1명, 김무선 | 저압 케이블 풀링 |  | TY25-004 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-27T08:36:51.321209 | 2026-05-27 17:36:51 | N
283 | 2026-05-28 |  | 단가 장비, 인원 점검(16시) | 이한열, 김국진 |  |  |  | 주간 | 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-27T08:37:25.432052 | 2026-05-27 17:37:25 | N
298 | 2026-05-29 |  | 광명 역세권 지구 저압 접속함 점검 | 이한열, 한동근, 변산 2명 |  |  | CG026-008 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-28T09:34:50.887563 | 2026-05-28 18:34:50 | N
307 | 2026-05-29 |  | 군포중 주변 지중화(총가) | 임재홍, 김종인, 최정우, 김기태, 김국진, 김성훈, 모범 1명, 김무선 | -저압 케이블 풀링 |  | TY25-004 | 주간 | 공사 일정 | manual |  | 0 |  |  |  | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-28T09:34:59.573268 | 2026-05-28 18:34:59 | N
45 | 2099-12-31 | 테스트현장 | 테스트작업 | [5 empty] | 공사 일정 | manual |  | 0 |  |  |  | test | test | 2026-03-27T08:06:40.852145 | 2026-03-27 17:06:40 | N

## 공사일정_핵심
id | date | location | task | details | person | tags | category | is_deleted | deleted_at | deleted_by | delete_reason | last_actor_user | last_actor_at | created_at
60 | 2026-03-07 |  | 연화TR67 -> 접속, 진단, 송전(3구간) |  |  |  | 일반 작업 | Y | 2026-03-31T06:41:38.920310 | admin | 현황판 인라인 삭제 | admin | 2026-03-31T06:41:38.920310 | 2026-03-31 08:41:14
13 | 2026-03-25 | 미정 | 정우전설 대표님 미팅 | 오후 4시 미팅 | 정우전설 대표님 |  | 일반메모 | Y | 2026-03-26T06:18:57.235395 | admin |  | admin | 2026-03-26T06:18:57.235395 | 2026-03-25 13:43:43
10 | 2026-03-26 | 연산동 | 플러그링크 굴착 |  | 미지정 | 야간 | 공사일정 | Y | 2026-03-26T08:12:06.963640 | admin | 현황판 인라인 삭제 | admin | 2026-03-26T08:12:06.963640 | 2026-03-25 11:20:03
11 | 2026-03-26 | 샘모루 초교 | 케이블 포설 | 심야 작업 |  | 야간 | 공사일정 | Y | 2026-03-26T04:49:27.365175 | admin |  | admin | 2026-03-26T04:49:27.365175 | 2026-03-25 11:21:15
12 | 2026-03-26 | 초평동 | 지중 전력 선로 가압 및 케이블 포설 입상 작업 |  |  |  | 공사일정 | Y | 2026-03-26T08:13:16.228379 | admin | 현황판 인라인 삭제 | admin | 2026-03-26T08:13:16.228379 | 2026-03-25 11:22:18
14 | 2026-03-26 |  |  |  | 전자칠판 |  | 공사일정 | Y | 2026-03-26T06:55:37.004306 | admin | 현황판 인라인 삭제 | admin | 2026-03-26T06:55:37.004306 | 2026-03-26 13:24:41
15 | 2026-03-26 | 안양 | 야간작업 |  | - |  | 공사일정 | Y | 2026-03-26T04:48:01.523619 | admin |  | admin | 2026-03-26T04:48:01.523619 | 2026-03-26 13:47:00
16 | 2026-03-26 | 군포 | 지중화 공사 |  | - |  | 공사일정 | Y | 2026-03-26T06:19:19.678838 | admin |  | admin | 2026-03-26T06:19:19.678838 | 2026-03-26 13:51:34
18 | 2026-03-26 | 안양중 | 포설 공사 | 2026년 3월 26일부터 31일까지 진행되는 심야 포설 공사 일정입니다. |  | 심야 | 공사일정 | Y | 2026-03-26T08:13:12.687789 | admin | 현황판 인라인 삭제 | admin | 2026-03-26T08:13:12.687789 | 2026-03-26 13:55:54
24 | 2026-03-26 | 안양 | NDLS 사진 촬영 |  | 임재홍, 김성훈 |  | 일반 작업 | N |  |  |  | 조성현 | 2026-03-27T06:44:11.371895 | 2026-03-27 11:44:18
46 | 2026-03-26 | 안양 | 샘모루초교 케이블 포설(심야) |  |  |  | 일반 작업 | Y | 2026-03-27T08:07:55.409664 | 조성현 | 현황판 인라인 삭제 | 조성현 | 2026-03-27T08:07:55.410664 | 2026-03-27 17:07:50
47 | 2026-03-26 |  | 현장답사 |  |  |  | 일정 | N |  |  |  | 전자칠판 | 2026-03-27T08:08:16.053987 | 2026-03-27 17:08:16
23 | 2026-03-26 | 안양 | 샘모루초교 케이블 포설(심야) | 변산 2명, 모범 1명 | 임재홍, 최정우, 김기태, 김국진, 김성훈, 김종인, 한동근 |  | 공사 일정 | N |  |  |  | 조성현 | 2026-03-27T08:10:58.406795 | 2026-03-27 17:10:58
17 | 2026-03-27 | 군포중 | 지중화 공사 추가작업 | 야간 추가작업 |  | 야간 | 공사일정 | Y | 2026-03-26T06:18:38.391495 | admin |  | admin | 2026-03-26T06:18:38.392497 | 2026-03-26 13:55:04
19 | 2026-03-27 | 군포 | 지중화 공사 | 야간 지중화 공사 |  | 야간 | 공사일정 | Y | 2026-03-26T06:18:25.482488 | admin |  | admin | 2026-03-26T06:18:25.482488 | 2026-03-26 14:15:41
20 | 2026-03-27 | 군포중 | 케이블 접속작업 |  |  |  | 공사일정 | Y | 2026-03-26T08:57:40.618767 | admin | 현황판 인라인 삭제 | admin | 2026-03-26T08:57:40.618767 | 2026-03-26 16:40:02
21 | 2026-03-27 | 샘모루초교 케이블 포설(심야) | 안양 비산동 | 김T | 전자칠판 |  | 공사일정 | Y | 2026-03-26T08:54:47.108767 | admin | 현황판 인라인 삭제 | admin | 2026-03-26T08:54:47.108767 | 2026-03-26 17:16:10
28 | 2026-03-27 | 검증현장A | [검증] 공사일정 담당자공란 | auto-check |  | check | 공사일정 | Y | 2026-03-27T02:38:51.817674 | verify_user | 자동검증 정리 | verify_user | 2026-03-27T02:38:51.817674 | 2026-03-27 11:38:51
29 | 2026-03-27 |  | [검증] 일반작업 등록 | auto-check | 전자칠판 |  | 일반 작업 | Y | 2026-03-27T02:38:51.833674 | verify_user | 자동검증 정리 | verify_user | 2026-03-27T02:38:51.833674 | 2026-03-27 11:38:51
30 | 2026-03-27 | 검증현장A | [검증2] 공사일정 담당자공란 | auto-check |  | check | 공사일정 | Y | 2026-03-27T02:39:24.146060 | verify_user | 자동검증 정리 | verify_user | 2026-03-27T02:39:24.146060 | 2026-03-27 11:39:24
31 | 2026-03-27 |  | [검증2] 일반작업 등록 | auto-check |  |  | 일반 작업 | Y | 2026-03-27T02:39:24.166239 | verify_user | 자동검증 정리 | verify_user | 2026-03-27T02:39:24.166239 | 2026-03-27 11:39:24
32 | 2026-03-27 | 안양 비산 | 1 | 1 |  |  | 공사일정 | Y | 2026-03-27T02:46:56.123035 | admin | 현황판 인라인 삭제 | admin | 2026-03-27T02:46:56.123035 | 2026-03-27 11:46:46
33 | 2026-03-27 |  | 저압 단가 |  | 임재홍, 이한열 |  | 일반 작업 | N |  |  |  | 조성현 | 2026-03-27T06:44:11.371895 | 2026-03-27 11:48:04
34 | 2026-03-27 |  | 자재 여입 |  | 임재홍, 이한열 |  | 일반 작업 | N |  |  |  | 조성현 | 2026-03-27T06:44:11.371895 | 2026-03-27 11:48:09
22 | 2026-03-27 | 안양 비산 | 샘모루초교 케이블 포설(심야) | 변산2명, 모범 1명 | 최정우, 김국진, 김성훈, 김종인, 한동근 |  | 공사 일정 | N |  |  |  | 조성현 | 2026-03-27T08:40:52.357411 | 2026-03-27 17:40:52
44 | 2026-03-28 | 군포 | 지중화 공사 |  |  |  | 공사일정 | Y | 2026-03-27T04:49:59.142008 | 상황판 | 현황판 인라인 삭제 | 상황판 | 2026-03-27T04:49:59.142008 | 2026-03-27 13:43:55
48 | 2026-03-28 | 안양 | 샘모루초교 케이블 포설(심야) |  |  |  | 일정 | Y | 2026-03-27T08:09:09.550705 | 조성현 | 현황판 인라인 삭제 | 조성현 | 2026-03-27T08:09:09.550705 | 2026-03-27 17:09:05
49 | 2026-03-28 | 안양 | 샘모루초교 케이블 포설(심야) |  |  |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-03-27T08:09:12.674713 | 2026-03-27 17:09:12
50 | 2026-03-28 | 안양 | 돌발대기 |  | 이한열, 김기태 |  | 일정 | N |  |  |  | 조성현 | 2026-03-27T08:17:10.862150 | 2026-03-27 17:17:10
26 | 2026-03-30 | 군포중 지중화 입상 케이블 포설 | 군포 | 이T, 최T, 김T, 김CJ, 김GI, 김GS, 모범 1명 | 전자칠판 |  | 공사일정 | Y | 2026-03-26T09:16:29.954371 | admin | 현황판 인라인 삭제 | admin | 2026-03-26T09:16:29.954371 | 2026-03-26 18:15:18
35 | 2026-03-30 |  | 저압 단가 | CO35 x 4L x 15mm 실리콘 접속제 | 이한열, 한동근 |  | 일반 작업 | N |  |  |  | 조성현 | 2026-03-27T06:44:11.371895 | 2026-03-27 11:49:42
25 | 2026-03-30 | 군포 | 군포중 지중화 입상 케이블 포설 | AL450x2개소, 접속원 투입 모범 1명 | 임재홍, 최정우, 김국진, 김기태, 김성훈, 김종인, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-03-31T06:57:49.566971 | 2026-03-31 15:57:49
37 | 2026-03-31 |  | 광명 역세권지구 저압신규 1건(오후 2시 이후) |  | 임재홍, 한동근 |  | 일반 작업 | N |  |  |  | 조성현 | 2026-03-27T06:44:11.371895 | 2026-03-27 11:52:00
77 | 2026-03-31 |  | 325 SQ 300m x 6 07:30 입고 (현대 건설 외상고장) 지게차 010-9141-9214 |  |  |  | 일정 | N |  |  |  | 전자칠판 | 2026-03-31T06:46:46.857813 | 2026-03-31 15:46:46
27 | 2026-03-31 | 군포 | 군포중 지중화 입상 케이블 포설 | 모범 1명 | 이한열, 최정우, 김국진, 김기태, 김성훈, 김종인, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-03-31T06:51:02.569397 | 2026-03-31 15:51:02
36 | 2026-03-31 |  | 공동구 현장 조사 | 09:30 공동구 관리 사무소 | 임재홍, 김도윤, 김상훈, 김무선 |  | 일반 작업 | N |  |  |  | admin | 2026-03-31T06:51:21.430581 | 2026-03-31 15:51:21
51 | 2026-04-01 | 안양 | 특별 회의 안전 교육 |  |  |  | 일정 | Y | 2026-03-30T06:14:47.665357 | 조성현 | 현황판 인라인 삭제 | 조성현 | 2026-03-30T06:14:47.665357 | 2026-03-27 17:18:47
53 | 2026-04-01 |  | 325 SQ 300m x 6 07:30 입고 (현대 건설 외상고장) 지게차 010-9141-9214 |  |  |  | 일정 | Y | 2026-03-31T06:47:20.054199 | admin | 현황판 인라인 삭제 | admin | 2026-03-31T06:47:20.054199 | 2026-03-27 17:31:40
39 | 2026-04-01 | 안산 | 안산 데이터 센터 방문 |  | 김무선, 김단후 |  | 일정 | N |  |  |  | admin | 2026-03-31T06:45:59.858925 | 2026-03-31 15:45:59
78 | 2026-04-01 |  | TR 955a - 500m x 6D 07:30 입고 (호계동 533-1) | 지게차 02 -742- 1395 |  |  | 일정 | N |  |  |  | admin | 2026-03-31T06:49:27.765406 | 2026-03-31 15:49:27
38 | 2026-04-01 |  | 안양 노후 케이블 교체 공사 | (연화 s/w 87 #1 ~ 연화 s/w 83 #3 1구간 약 26cm) 변산 2, 모범 2 | 임재홍, 최정우, 김국진, 한동근, 김상훈 |  | 공사 일정 | N |  |  |  | admin | 2026-04-03T09:02:13.143413 | 2026-04-03 18:02:13
52 | 2026-04-01 |  | 호계동 만안교통 신설 | 관로(0,2,0) 역 28M(보도), TR 300KWA, 1대 T3-L 1조, 변산 3명, 모범 1명, 3W, 15t 덤프 | 이한열, 김성훈, 김종인, 김기태, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-03T09:02:17.429663 | 2026-04-03 18:02:17
57 | 2026-04-02 |  | 특별 회의 안전 교육(안양지사) 15:00~ |  | 이한열, 김국진, 김성훈, 김종인, 김무선, 김도윤, 김상훈, 이재규, 김단후 |  | 일정 | N |  |  |  | admin | 2026-04-03T05:36:31.662349 | 2026-04-03 14:36:31
42 | 2026-04-02 |  | 광명 단가 기기 교체 | 1. 광덕 TR7-P2 3상 300Kva -> 3상 300Kva -> 23시 ~ 01시 무정전 2. 소라TR 158-P4 3상 200Kva -> 3상 300Kva -> 01시 ~ 03시 -> 발전기 필요(신호등) 무정전 3. 소라 TR 161-P5 3상 75Kva -> 3상 75Kva -> 03시 ~ 05시 무정전 | 임재홍, 김국진, 한동근, 김상훈 |  | 공사 일정 | N |  |  |  | admin | 2026-04-03T08:45:41.181414 | 2026-04-03 17:45:41
41 | 2026-04-02 |  | 군포중 지중화 케이블 포설(AL40 x 1개소) |  | 김무선, 임재홍, 이한열, 최정우, 김종인, 김성훈, 김국진, 김기태, 한동근 |  | 공사 일정 | N |  |  |  | admin | 2026-04-03T09:02:24.117486 | 2026-04-03 18:02:24
43 | 2026-04-02 |  | 안양 케이블 교체 -> 접속, 진단, 송전 |  | 김상훈 |  | 공사 일정 | N |  |  |  | admin | 2026-04-06T23:58:49.606354 | 2026-04-07 08:58:49
82 | 2026-04-03 |  | 아침 7시 특고 케이블 AL95SQ * 600m * 3d 입고예정 |  |  |  | 일정 | N |  |  |  | 전자칠판 | 2026-03-31T08:57:07.329030 | 2026-03-31 17:57:07
56 | 2026-04-03 |  | 안양지사 착수회의 신촌 s/w 71 기간만료 오전 10시 |  | 김도윤 |  | 일정 | N |  |  |  | 조성현 | 2026-04-01T09:32:31.828248 | 2026-04-01 18:32:31
94 | 2026-04-03 | 현장 사무실 | 회의 | 오후 4시 회의 진행 |  | 회의 | 일반메모 | Y | 2026-04-03T08:36:38.124464 | admin | 현황판 인라인 삭제 | admin | 2026-04-03T08:36:38.124486 | 2026-04-03 15:03:00
40 | 2026-04-03 |  | 샘모루 초교 입상 케이블 포설 2개소 | 영전사 접속 변산 2명, 모범 1명 | 김국진, 최정우, 김성훈, 김기태, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-04-03T09:02:42.659201 | 2026-04-03 18:02:42
88 | 2026-04-04 |  | 관로구방수장치 시공 (150파이 4개) | 임태욱소장 실행팀 진행 | 김단후 |  | 공사 일정 | N |  |  |  | admin | 2026-04-03T09:02:36.132927 | 2026-04-03 18:02:36
69 | 2026-04-06 |  | 김성훈 연차 |  |  |  | 일정 | Y | 2026-04-06T01:18:56.131733 | admin | 현황판 인라인 삭제 | admin | 2026-04-06T01:18:56.131756 | 2026-03-31 15:34:24
102 | 2026-04-06 |  | 단가 현장 답사 | 개폐기 교체 준비 | 임재홍 |  | 일정 | Y | 2026-04-05T23:42:14.088050 | admin | 현황판 인라인 삭제 | admin | 2026-04-05T23:42:14.088072 | 2026-04-06 08:41:51
54 | 2026-04-06 |  | 연화 TR67 외 26년 경과 노후 변압기 선로 교체공사 | -연화 s/w 40 #3 ~ 연화 s/w 44 #2 - CN 60 -> AL 95 약 250m (3구간) 변산 2명, 모범 2명 | 임재홍, 최정우, 김국진, 김기태, 한동근, 김상훈 |  | 공사 일정 | N |  |  |  | admin | 2026-04-07T07:21:50.311836 | 2026-04-07 16:21:50
55 | 2026-04-06 |  | 호계동 만안 교통 접속 | 직선(75) 1조, 엘보(변60) 3조 오륜전기 | 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-07T07:22:07.329704 | 2026-04-07 16:22:07
72 | 2026-04-06 |  | 광명 역세권 기기 점검 예정 | 변산 2명 | 이한열, 김종인,김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-04-15T01:52:00.676704 | 2026-04-15 10:52:00
65 | 2026-04-07 |  | 김성훈 연차 |  |  |  | 일정 | Y | 2026-04-06T01:15:28.085995 | 상황판 | 현황판 인라인 삭제 | 상황판 | 2026-04-06T01:15:28.086019 | 2026-03-31 15:31:51
84 | 2026-04-07 |  | 변압기 입고 07:30 TR150Kva 4eu | 지게차 010-5710-4725 광명단가 |  |  | 일정 | N |  |  |  | admin | 2026-04-02T00:07:39.921253 | 2026-04-02 09:07:39
86 | 2026-04-07 |  | 만인 sw10 지상 개폐기 교체 공사 09:00 ~ 11:00 |  |  |  | 공사 일정 | Y | 2026-04-02T23:44:29.763874 | admin | 현황판 인라인 삭제 | admin | 2026-04-02T23:44:29.763893 | 2026-04-03 08:44:21
62 | 2026-04-07 |  | 군포중 지중화 직선 접속 |  | 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-04-03T08:50:31.629303 | 2026-04-03 17:50:31
61 | 2026-04-07 |  | 연화TR67 -> 접속, 진단, 송전(3구간) |  | 김상훈 |  | 공사 일정 | N |  |  |  | admin | 2026-04-03T09:02:53.766963 | 2026-04-03 18:02:53
101 | 2026-04-07 |  | 초평동 한국토지주택공사 가로등(을) 1kw 신설(상용/임시)_3058 |  |  |  | 공사 일정 | N |  |  |  | admin | 2026-04-03T09:02:57.852880 | 2026-04-03 18:02:57
83 | 2026-04-07 |  | 광명, 안양 저압단가 |  | 최정우, 김국진, 이재규 |  | 공사 일정 | N |  |  |  | 상황판 | 2026-04-06T01:16:32.741641 | 2026-04-06 10:16:32
114 | 2026-04-07 |  | 케이블 교체 준비 |  | 임재홍, 최정우, 김국진 |  | 일정 | N |  |  |  | admin | 2026-04-06T09:09:37.610842 | 2026-04-06 18:09:37
58 | 2026-04-07 |  | 군포중 지중화 케이블포설(m/H~입상) | 변산 3명, 모범 1명 | 김종인, 이한열, 김국진, 김기태, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-04-07T00:08:18.519953 | 2026-04-07 09:08:18
85 | 2026-04-07 |  | 단가 현장 답사 |  | 임재홍 |  | 일정 | N |  |  |  | 조성현 | 2026-04-07T01:40:50.084286 | 2026-04-07 10:40:50
100 | 2026-04-07 |  | 초평동599-25 한국토지주택공사 가로등(을) 2kw 신설(상용/임시)_3059 |  |  |  | 공사 일정 | N |  |  |  | 조성현 | 2026-04-07T01:41:01.694005 | 2026-04-07 10:41:01
73 | 2026-04-07 |  | 광명 역세권 기기 점검 |  | 이한열, 김종인, 한동근, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-04-15T01:52:04.222690 | 2026-04-15 10:52:04
74 | 2026-04-08 |  | 광명 역세권 기기 점검 예정 |  |  |  | 일정 | Y | 2026-04-02T23:48:12.424350 | admin | 현황판 인라인 삭제 | admin | 2026-04-02T23:48:12.424372 | 2026-03-31 15:40:46
80 | 2026-04-08 |  | 안양 샘모루 초교 케이블 포설 | 변산 2명, 모범 1명 | 김성훈, 이한열, 김종인, 김국진, 김기태, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-04-03T08:50:59.253300 | 2026-04-03 17:50:59
59 | 2026-04-08 |  | 군포중 지중화 케이블종단 입상 2개소 | 접속 - 영전사 | 임재홍, 최정우, 김성훈, 한동근, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-04-07T06:30:27.520972 | 2026-04-07 15:30:27
63 | 2026-04-08 |  | 군포중 지중화 직선 접속 | 모범 1 접속(오륜전기) - 직선 | 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-08T00:59:06.796798 | 2026-04-08 09:59:06
70 | 2026-04-09 |  | 초평동 지ㆍ전 선로가압, 종단 케이블 재4/신설 |  | 김무선 |  | 공사 일정 | Y | 2026-03-31T08:49:57.250673 | admin | 현황판 인라인 삭제 | admin | 2026-03-31T08:49:57.250673 | 2026-03-31 15:38:18
75 | 2026-04-09 |  | 광명 역세권 기기 점검 예정 |  |  |  | 일정 | Y | 2026-04-02T23:48:51.472322 | admin | 현황판 인라인 삭제 | admin | 2026-04-02T23:48:51.472345 | 2026-03-31 15:40:54
66 | 2026-04-09 |  | 이한열 연차 |  |  |  | 일정 | Y | 2026-04-06T01:52:03.732850 | admin | 현황판 인라인 삭제 | admin | 2026-04-06T01:52:03.732873 | 2026-04-03 17:38:43
71 | 2026-04-09 |  | 안양 샘모루 초교 지중화 케이블 포설 | 변산 3명, 모범 1명 | 김성훈, 김종인, 김국진, 김기태 |  | 공사 일정 | N |  |  |  | admin | 2026-04-03T08:51:07.047373 | 2026-04-03 17:51:07
110 | 2026-04-09 |  | 안양 샘모루 케이블 포설 mcm | 자재수령, 안양지사 325SQ 300 x 3 입고 |  |  | 일정 | Y | 2026-04-06T09:04:07.774698 | admin | 현황판 인라인 삭제 | admin | 2026-04-06T09:04:07.774716 | 2026-04-06 18:03:51
112 | 2026-04-09 |  | 95SQ 500m x 6 07:30 입고 (안양단가) | 지게차 010-4492-9030 |  |  | 일정 | N |  |  |  | 전자칠판 | 2026-04-06T09:05:43.979825 | 2026-04-06 18:05:43
111 | 2026-04-09 |  | 자재수령, 안양지사 325SQ 300m x 3 입고 |  |  |  | 일정 | N |  |  |  | admin | 2026-04-06T09:05:53.372883 | 2026-04-06 18:05:53
113 | 2026-04-09 |  | 대농 m/m2 : 4va 재설치, 현장조사(오후) | 지게차 010-4492-9030 | 임재홍, 최정우, 한동근 |  | 일정 | N |  |  |  | admin | 2026-04-06T09:07:40.189029 | 2026-04-06 18:07:40
87 | 2026-04-09 |  | 만인 sw10 지상 개폐기 교체 공사 09:00 ~ 11:00 | 대농 M/N2 : 4va 재설치, 현장조사(오후) | 임재홍, 최정우, 한동근, 김도윤 |  | 공사 일정 | N |  |  |  | 조성현 | 2026-04-07T01:33:54.960450 | 2026-04-07 10:33:54
64 | 2026-04-09 |  | 군포중 지중화 직선 접속 | 모범 1 | 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-07T07:20:48.704125 | 2026-04-07 16:20:48
67 | 2026-04-10 |  | 군포중 지중화 직선 접속(야간) |  |  |  | 공사 일정 | Y | 2026-04-02T23:56:01.115060 | admin | 현황판 인라인 삭제 | admin | 2026-04-02T23:56:01.115083 | 2026-03-31 15:33:02
76 | 2026-04-10 |  | 광명 역세권 기기 점검 예정 |  |  |  | 일정 | Y | 2026-04-02T23:48:55.090039 | admin | 현황판 인라인 삭제 | admin | 2026-04-02T23:48:55.090060 | 2026-03-31 15:41:00
81 | 2026-04-10 |  | 안양 샘모루 초교 케이블 포설(야간) |  |  |  | 공사 일정 | Y | 2026-04-02T23:56:04.189922 | admin | 현황판 인라인 삭제 | admin | 2026-04-02T23:56:04.189944 | 2026-03-31 17:52:06
79 | 2026-04-10 |  | 초평동 지ㆍ전 선로가압, 입상 케이블 철거/재사, 26호 종단 케이블 철거 | 3w : 오전 0.5 접속 - 영전사 변산 2명, 모범 1명 | 임재홍, 최정우, 이한열, 한동근, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-04-07T06:31:21.438575 | 2026-04-07 15:31:21
121 | 2026-04-10 |  | 광명 역세권 지구 기기점검(신호기) |  | 이한열, 김종인, 김기태, 한동근 |  | 공사 일정 | Y | 2026-04-10T06:37:00.370655 | admin | 현황판 인라인 삭제 | admin | 2026-04-10T06:37:00.370678 | 2026-04-08 09:32:40
134 | 2026-04-10 |  | 투개방 + 엘보분리 13:00 |  | 이재규 |  | 일정 | N |  |  |  | admin | 2026-04-09T23:34:52.899170 | 2026-04-10 08:34:52
97 | 2026-04-13 |  | 비산동1111 한국환경공단 210kW 신설_3788 |  |  |  | 공사 일정 | Y | 2026-04-15T00:24:22.120758 | 김명호 | 현황판 인라인 삭제 | 김명호 | 2026-04-15T00:24:22.120781 | 2026-04-03 18:04:12
98 | 2026-04-13 |  | 광명동 광명3동복합청사 고압 800KW 신설(광덕SW10-1) |  | 이한열, 김종인, 김기태, 한동근 |  | 공사 일정 | Y | 2026-04-15T00:24:07.757550 | 김명호 | 현황판 인라인 삭제 | 김명호 | 2026-04-15T00:24:07.757573 | 2026-04-08 18:34:29
89 | 2026-04-13 |  | 연화 TR67외 26년 경과 노후 케이블 교체 공사 CE60 -> AL95 | 연화 s/w 38 #1 ~ 연화 TR 67 HA -> 약 80m 변산 2명, 모범 1명 | 김상훈, 임재홍, 최정우, 김성훈, 김국진 |  | 공사 일정 | N |  |  |  | admin | 2026-04-12T23:51:59.982195 | 2026-04-13 08:51:59
137 | 2026-04-13 |  | 광명 역세권 지구 기기점검(삼천리) |  | 이한열, 김종인, 김기태, 한동근 |  | 공사 일정 | N |  |  |  | admin | 2026-04-15T01:52:33.562812 | 2026-04-15 10:52:33
90 | 2026-04-14 |  | 부림 s/w 53 외 26년 경과 노후 케이블 교체 공사 | 목련 s/w 33 #1 ~ 목련 s/w 45 #1 -> 약 220m | 김상훈 |  | 공사 일정 | Y | 2026-04-15T00:24:51.405838 | 김명호 | 현황판 인라인 삭제 | 김명호 | 2026-04-15T00:24:51.405860 | 2026-04-07 15:36:22
118 | 2026-04-14 |  | 케이블 접속, 진단, 송전 - 부림 s/w 33 |  |  |  | 공사 일정 | Y | 2026-04-07T07:19:45.918868 | admin | 현황판 인라인 삭제 | admin | 2026-04-07T07:19:45.918890 | 2026-04-07 16:19:39
117 | 2026-04-14 |  | 케이블 접속, 진단, 송전 - 연화 s/w 42 |  | 김도윤 |  | 공사 일정 | Y | 2026-04-15T01:38:02.583105 | admin | 현황판 인라인 삭제 | admin | 2026-04-15T01:38:02.583129 | 2026-04-07 16:20:11
122 | 2026-04-14 |  | 안양 저압 단가 |  |  |  | 공사 일정 | Y | 2026-04-15T01:39:39.713639 | admin | 현황판 인라인 삭제 | admin | 2026-04-15T01:39:39.713661 | 2026-04-08 09:33:19
91 | 2026-04-14 |  | 군포중 지중화 직선접속 | 모범1 |  |  | 공사 일정 | Y | 2026-04-15T01:38:55.687371 | admin | 현황판 인라인 삭제 | admin | 2026-04-15T01:38:55.687392 | 2026-04-08 09:33:40
131 | 2026-04-14 |  | 2번 크레인 안전검사 14:00 (오룡) |  | 이한열, 한동근 |  | 일정 | Y | 2026-04-15T01:38:24.767655 | admin | 현황판 인라인 삭제 | admin | 2026-04-15T01:38:24.767676 | 2026-04-10 08:37:09
138 | 2026-04-14 |  | 테스트 | 테스트중입니다 |  |  | 일반 작업 | Y | 2026-04-15T01:37:48.633744 | admin | 현황판 인라인 삭제 | admin | 2026-04-15T01:37:48.633765 | 2026-04-13 09:08:36
120 | 2026-04-14 |  | 평촌동 895 한국 환경 공단 신설 | - 도로 컷팅 : 40m x 2줄 | 임재홍, 최정우, 김성훈, 김국진, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-15T01:41:14.671116 | 2026-04-15 10:41:14
146 | 2026-04-14 |  | 2번 크레인 안전검사 14:00 | -호룡사업소 |  |  | 일정 | N |  |  |  | admin | 2026-04-15T01:43:02.110461 | 2026-04-15 10:43:02
147 | 2026-04-14 |  | 변압기 오일 펜스 설치 |  |  |  | 일정 | N |  |  |  | admin | 2026-04-15T01:49:05.578351 | 2026-04-15 10:49:05
148 | 2026-04-14 |  | 광명 삼천리 기기점검 | 개폐기 | 이한열, 김종인, 김기태, 한동근, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-04-15T01:51:53.609036 | 2026-04-15 10:51:53
145 | 2026-04-14 |  | 대농 2 맨홀 저압 보수 | - 4um 설치 및 점퍼선 설치 | 최정우, 김성훈, 김국진, 김상훈 |  | 공사 일정 | N |  |  |  | admin | 2026-04-15T01:52:51.317028 | 2026-04-15 10:52:51
140 | 2026-04-14 |  | 안양 샘모루 지중화 | 고압접속 오륜전기 2명 | 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-04-16T09:20:17.010125 | 2026-04-16 18:20:17
68 | 2026-04-15 |  | 82저 1112 크레인 안전검사 14:00 - 호룡수도권 사업소 |  |  |  | 일정 | N |  |  |  | 전자칠판 | 2026-03-31T06:34:07.369994 | 2026-03-31 15:34:07
96 | 2026-04-15 |  | 고천동227-4 고천프라자 350kW 신설_3762 |  |  |  | 공사 일정 | Y | 2026-04-15T01:34:48.163102 | admin | 현황판 인라인 삭제 | admin | 2026-04-15T01:34:48.163125 | 2026-04-03 18:04:28
107 | 2026-04-15 |  | 부림 s/w 53 외 26년 경과 노후 케이블 교체 공사 | 목련 TR 33 HB ~ 신촌 s/w 16 #1 -> 약 186m |  |  | 공사 일정 | Y | 2026-04-06T09:01:33.855563 | admin | 현황판 인라인 삭제 | admin | 2026-04-06T09:01:33.855586 | 2026-04-06 18:01:24
106 | 2026-04-15 |  | 부림 s/w 53 외 26년 경과 노후 케이블 교체 공사 | 부림 TR28 HB ~ 부림 s/w 72 #1 -> 약 95m | 김상훈 |  | 공사 일정 | Y | 2026-04-15T00:28:11.795402 | 김명호 | 현황판 인라인 삭제 | 김명호 | 2026-04-15T00:28:11.795423 | 2026-04-07 08:41:01
119 | 2026-04-15 |  | 케이블 접속, 진단, 송전 - 부림 s/w 33 |  | 김상훈 |  | 공사 일정 | Y | 2026-04-15T01:33:32.801993 | admin | 현황판 인라인 삭제 | admin | 2026-04-15T01:33:32.802017 | 2026-04-07 16:20:04
92 | 2026-04-15 |  | 군포중 지중화 직선접속 | 모범1 |  |  | 공사 일정 | Y | 2026-04-15T01:33:27.831066 | admin | 현황판 인라인 삭제 | admin | 2026-04-15T01:33:27.831089 | 2026-04-08 09:34:19
116 | 2026-04-15 |  | 평촌동 895 한국 환경 공단 신설 | - 기초대 설치 : T-3L x 1조 - 관로굴착(도로 횡단) : 약 40m(0, 2, 0) | 이한열, 김성훈, 김종인, 김기태 |  | 공사 일정 | N |  |  |  | admin | 2026-04-15T01:36:18.379892 | 2026-04-15 10:36:18
115 | 2026-04-15 |  | 비산동 1111 한국환경공단신설 | -관로 굴착(보도) : 20m (0, 0, 2) -보도 복구 : 1m x 20m -케이블 풀링(cv240x3, 120x1) : 약 25m -저압접속 : 동관 . BL | 임재홍, 최정우, 김성훈, 김종인, 김국진, 김기태, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-15T01:53:08.137179 | 2026-04-15 10:53:08
132 | 2026-04-15 |  | 저압단가(초평동)-16개소 |  | 이한열, 한동근, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-15T02:50:48.349909 | 2026-04-15 11:50:48
93 | 2026-04-16 |  | 군포중 지중화 직선접속 |  |  |  | 공사 일정 | Y | 2026-04-15T01:37:27.665244 | admin | 현황판 인라인 삭제 | admin | 2026-04-15T01:37:27.665265 | 2026-04-03 17:56:04
109 | 2026-04-16 |  | 안양 샘모루 케이블 포설 mcm |  |  |  | 공사 일정 | Y | 2026-04-06T09:02:01.267485 | admin | 현황판 인라인 삭제 | admin | 2026-04-06T09:02:01.267507 | 2026-04-06 18:01:53
108 | 2026-04-16 |  | 부림 s/w 53 외 26년 경과 노후 케이블 교체 공사 | 목련 TR 33 HB ~ 신촌 s/w 16 #1 -> 약 186m | 김상훈 |  | 공사 일정 | Y | 2026-04-15T01:29:43.129276 | admin | 현황판 인라인 삭제 | admin | 2026-04-15T01:29:43.129298 | 2026-04-07 08:41:07
105 | 2026-04-16 |  | 안양 샘모루 케이블 포설 MCM |  |  |  | 공사 일정 | Y | 2026-04-09T23:33:06.584665 | admin | 현황판 인라인 삭제 | admin | 2026-04-09T23:33:06.584686 | 2026-04-07 08:43:36
139 | 2026-04-16 |  | 야적장 점검(오전) |  |  |  | 일정 | N |  |  |  | admin | 2026-04-15T01:37:02.964277 | 2026-04-15 10:37:02
123 | 2026-04-16 |  | 연화 TR67 외 26년 경과 노후 케이블 교체 공사 | -구간: 연화 s/w 42 #1 ~ 연화 s/w96 #3(cn50 -> ca95) : 180m -접속(오륜전기) : 직선 95x1조, 데드 95x2조 변산 2명, 모범 2명, 오륜전기 2명 | 임재홍, 최정우, 김국진, 한동근, 김상훈 |  | 공사 일정 | N |  |  |  | admin | 2026-04-15T23:50:28.612154 | 2026-04-16 08:50:28
124 | 2026-04-16 |  | 평촌동 895 한국 환경 공단 신설 | - 케이블 풀링(CA95) : 약 110m x 3D - 변압기 설치 : 31 300KVA x 1대 - 절체 및 케이블 절단 - 접속(오륜전기) : 직선95 x 2조, TR95 x 2조 모범 1명 | 이한열, 김성훈, 김종인, 김기태, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-15T23:54:03.830039 | 2026-04-16 08:54:03
95 | 2026-04-17 |  | 관양동1020-1 현대드림모터스 89kw 증설_3040 |  |  |  | 공사 일정 | Y | 2026-04-15T01:46:12.909534 | admin | 현황판 인라인 삭제 | admin | 2026-04-15T01:46:12.909556 | 2026-04-03 18:04:32
103 | 2026-04-17 |  | 최정우 연차 |  |  |  | 일정 | Y | 2026-04-06T01:52:00.242533 | admin | 현황판 인라인 삭제 | admin | 2026-04-06T01:52:00.242552 | 2026-04-06 08:54:00
129 | 2026-04-17 |  | 초평동599-25 한국토지주택공사 가로등(을) 2kw 신설(상용/임시)_3059 |  |  |  | 공사 일정 | Y | 2026-04-15T01:46:05.131628 | admin | 현황판 인라인 삭제 | admin | 2026-04-15T01:46:05.131650 | 2026-04-08 11:35:16
130 | 2026-04-17 |  | 초평동 한국토지주택공사 가로등(을) 1kw 신설(상용/임시)_3058 |  |  |  | 공사 일정 | Y | 2026-04-15T01:46:00.921580 | admin | 현황판 인라인 삭제 | admin | 2026-04-15T01:46:00.921603 | 2026-04-08 11:35:31
125 | 2026-04-17 |  | NDIS 사진 촬영 |  | 임재홍, 김국진, 한동근 |  | 일정 | Y | 2026-04-15T01:47:37.181297 | admin | 현황판 인라인 삭제 | admin | 2026-04-15T01:47:37.181320 | 2026-04-08 18:38:07
133 | 2026-04-17 |  | 안양 샘모루 초교 케이블 포설 | 변산 3명, 모범 1명 | 김성훈, 이한열, 김종인, 한동근 |  | 공사 일정 | Y | 2026-04-16T07:53:32.228600 | admin | 현황판 인라인 삭제 | admin | 2026-04-16T07:53:32.228623 | 2026-04-14 17:39:32
142 | 2026-04-17 |  | 광명 역세권 지구 기기점검(삼천리) |  |  |  | 공사 일정 | Y | 2026-04-14T23:46:43.095623 | admin | 현황판 인라인 삭제 | admin | 2026-04-14T23:46:43.095645 | 2026-04-15 08:46:26
149 | 2026-04-17 |  | 의왕 초평동 선로가압, 입상 케이블 철거/재사.종단 접속재 철거 | 변산 3명, 모범 1명 | 임재홍, 김국진, 한동근 |  | 공사 일정 | Y | 2026-04-16T07:50:55.615207 | admin | 현황판 인라인 삭제 | admin | 2026-04-16T07:50:55.615230 | 2026-04-15 10:47:09
141 | 2026-04-17 |  | 연화 TR67 외 26년 경과 노후 케이블 교체 공사 -> 절체지원 |  | 김상훈, 한동근 |  | 공사 일정 | N |  |  |  | admin | 2026-04-16T07:51:34.928187 | 2026-04-16 16:51:34
153 | 2026-04-17 |  | 비산동 샘모루 초교 주변 지중화(총가) | -고압케이블 풀링 -변산 3명 모범 1명 | 김성훈, 이한열, 김종인, 한동근 |  | 공사 일정 | N |  |  |  | admin | 2026-04-16T08:12:18.869466 | 2026-04-16 17:12:18
152 | 2026-04-17 |  | 초평동 한국주택공사 지,전(총가) | -케이블 철거 및 입상 철거((A400):40m -관로 굴착 및 기설관로 연결 -케이블 철거 및 재사 포설 -입상금구류철거 *케이블 절단 -변산 3명, 모범 1명 | 임재홍, 김국진, 한동근, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-04-16T08:12:34.320328 | 2026-04-16 17:12:34
154 | 2026-04-17 |  | 초평동 한국주택공사 지·전 (총가) | [팀] 공사1팀 케이블 철거 및 입상철거 (CA400): 40m, 관로 굴착 및 기설관로 연결 (311A x 1공), 케이블 철거 및 개소 도색 (CA400), 입상금구류 철거, *상추적 판별 케이블 절단 5톤 크레인, 1t, 1t 바가지 (실), 1번 카고, 5t 덤프, 3W-1대 (오후 05) | 임GS, 김GS, 한GS, 변전3명, 모바일1명, <김무성> |  | 공사 일정 | Y | 2026-04-17T07:30:24.867942 | admin | 현황판 인라인 삭제 | admin | 2026-04-17T07:30:24.867963 | 2026-04-17 14:45:01
155 | 2026-04-17 |  | 비산동 샘모루 초교 주변 지중화 (총가) | [팀] 공사2팀 4/17 ~ 4/18 (야간) 고압케이블 풀링 5톤 크레인, 1번 크레인, 1t, 더블캡 | 김TJ, 이TJ, 김CJ, 한GS, 변전3명, 모바일1명, <권우성> |  | 공사 일정 | Y | 2026-04-17T07:30:37.729467 | admin | 현황판 인라인 삭제 | admin | 2026-04-17T07:30:37.729489 | 2026-04-17 14:45:01
156 | 2026-04-17 |  | 케이블 교체 복구 절체 지원 | [팀] 공사3팀 (주간) (09:00) 더블캡 | 한GS, (김상훈) |  | 공사 일정 | Y | 2026-04-17T07:30:33.775285 | admin | 현황판 인라인 삭제 | admin | 2026-04-17T07:30:33.775307 | 2026-04-17 14:45:01
157 | 2026-04-17 |  | 최정우 TJ 연차 | [팀] 기타 (4/17, 4/20) | 최정우 TJ |  | 공사 일정 | Y | 2026-04-17T07:30:29.344495 | admin | 현황판 인라인 삭제 | admin | 2026-04-17T07:30:29.344516 | 2026-04-17 14:45:01
104 | 2026-04-20 |  | 최정우, 이한열 연차 |  |  |  | 일정 | Y | 2026-04-06T01:52:11.403052 | admin | 현황판 인라인 삭제 | admin | 2026-04-06T01:52:11.403075 | 2026-04-06 08:54:15
128 | 2026-04-20 |  | 비산동1111 한국환경공단 210kW 신설_3788 |  |  |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-04-08T02:34:38.012172 | 2026-04-08 11:34:38
150 | 2026-04-20 |  | 투개방 09:30(엘보분기필요) |  |  |  | 일정 | N |  |  |  | 전자칠판 | 2026-04-15T01:48:06.557531 | 2026-04-15 10:48:06
158 | 2026-04-20 |  | 광명 삼천리 기기점검 | [팀] 공사1팀 기기떼기 1t 바가지(주) | 김CJ, 한GS, 김우석 |  | 공사 일정 | Y | 2026-04-17T08:45:12.052763 | admin | 현황판 인라인 삭제 | admin | 2026-04-17T08:45:12.052784 | 2026-04-17 17:45:06
160 | 2026-04-20 |  | 만안 TR 24리 노후케이블 교체 (SJE) | [팀] 공사2팀 구간: 삼성 5/12 #1 ~ 삼성 TR 2 #4B (CNCV -> CA98) = 약 30m. 접속(오렌지): TR 1차 x 1조, 테이프 8자 x 2 5톤 크레인, 더블캡 (김상훈) | 김SJ, 김JS, 김GS, 김GS, 변전 2명, 보조 1명, 김상훈 |  | 공사 일정 | Y | 2026-04-17T08:45:35.893718 | admin | 현황판 인라인 삭제 | admin | 2026-04-17T08:45:35.893740 | 2026-04-17 17:45:06
161 | 2026-04-20 |  | NDIS 사진 촬영 | [팀] 공사2팀 NDIS 사진 촬영 | 김JS, 김GS, 변전 1명 |  | 공사 일정 | Y | 2026-04-17T08:45:56.629437 | admin | 현황판 인라인 삭제 | admin | 2026-04-17T08:45:56.629459 | 2026-04-17 17:45:06
164 | 2026-04-20 |  | NDIS 사진 촬영 | [팀] 공사3팀 NDIS 사진 촬영 더블캡 | 김TD, 김GS, 변전 1명, 김도윤 |  | 공사 일정 | Y | 2026-04-17T08:46:00.037893 | admin | 현황판 인라인 삭제 | admin | 2026-04-17T08:46:00.037914 | 2026-04-17 17:45:06
165 | 2026-04-20 |  | 연차 (4/20) | [팀] 기타 이한열 TS, 최정우 TS 연차 (4/20) | 이한열 TS, 최정우 TS |  | 공사 일정 | Y | 2026-04-17T08:45:47.633039 | admin | 현황판 인라인 삭제 | admin | 2026-04-17T08:45:47.633059 | 2026-04-17 17:45:06
163 | 2026-04-20 |  | 호계동 1223 홍재성 저압 | 인입선 접속 = BS x 4 더블캡 | 임재홍, 김국진, 변산 1명, 김도윤 |  | 공사 일정 | N |  |  |  | admin | 2026-04-17T08:46:59.592707 | 2026-04-17 17:46:59
162 | 2026-04-20 |  | 백운 5/12 #2 개방 및 일보분리 | [팀] 공사3팀 절연캡 시공 A상 1t | 김성훈, 김도윤 |  | 공사 일정 | N |  |  |  | admin | 2026-04-17T08:47:20.733137 | 2026-04-17 17:47:20
159 | 2026-04-20 |  | 광명 일직동 528-1 (삼천리 26-103) 저압 신규 | 접속함 접속 1t 바가지(주) | 김종인, 한동근, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-04-17T08:47:58.078012 | 2026-04-17 17:47:58
143 | 2026-04-20 |  | 광명 역세권 지구 기기점검(삼천리) | -개폐기 | 김종인, 한동근, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-04-19T23:39:41.929723 | 2026-04-20 08:39:41
136 | 2026-04-20 |  | 만안 TR 24 외 26년 경과 노후변압기 선로 교체공사 | 상성 s/w 12 # 1 -> 상성 TR2 HA | 임재홍,김성훈,김국진,김기태,변산2명,모범1명,김상훈 |  | 공사 일정 | N |  |  |  | admin | 2026-04-19T23:40:37.928430 | 2026-04-20 08:40:37
144 | 2026-04-20 |  | 안양 NDIS 사진 촬영 |  | 김성훈,김기태,변산1명,김상훈 |  | 일정 | N |  |  |  | admin | 2026-04-19T23:41:00.834274 | 2026-04-20 08:41:00
126 | 2026-04-21 |  | 고천동227-4 고천프라자 350kW 신설_3762 |  |  |  | 공사 일정 | Y | 2026-04-20T07:57:24.686539 | admin | 현황판 인라인 삭제 | admin | 2026-04-20T07:57:24.686560 | 2026-04-08 11:34:13
127 | 2026-04-21 |  | 비산동1111 한국환경공단 210kW 신설_3788 |  |  |  | 공사 일정 | Y | 2026-04-08T02:34:33.222613 | admin | 현황판 인라인 삭제 | admin | 2026-04-08T02:34:33.222636 | 2026-04-08 11:34:28
172 | 2026-04-21 |  | 안양 샘모루 초교 J/B 신설 (2개소) |  | 임재홍, 김성훈, 최정우, 김국진, 모범 1명 |  | 공사 일정 | Y | 2026-04-20T07:57:46.295220 | admin | 현황판 인라인 삭제 | admin | 2026-04-20T07:57:46.295242 | 2026-04-17 17:54:56
177 | 2026-04-21 |  | 케이블 입고 (07:00 창고) | [팀] 기타 CE 325 : 300m x 3D, 지게차 대여 : 010-8633-9325 | - |  | 공사 일정 | Y | 2026-04-20T07:55:52.404924 | admin | 현황판 인라인 삭제 | admin | 2026-04-20T07:55:52.404945 | 2026-04-20 16:52:45
174 | 2026-04-21 |  | 광명 삼천리 기기 점검 | 개폐기 - 2팀 1t (바가지-구) | 이한열, 김종인, 김기태, 한동근 |  | 공사 일정 | N |  |  |  | admin | 2026-04-20T07:53:50.548023 | 2026-04-20 16:53:50
173 | 2026-04-21 |  | 케이블 입고 07:00 입고 광명 단가 | CE325 : 300(m x 3D) 지게차 010-8633-9325 |  |  | 일정 | N |  |  |  | admin | 2026-04-20T07:55:47.802615 | 2026-04-20 16:55:47
175 | 2026-04-21 |  | 공드럼 반출 (우성목재) | 고압드럼 |  |  | 일정 | N |  |  |  | admin | 2026-04-20T07:57:00.539379 | 2026-04-20 16:57:00
176 | 2026-04-21 |  | 비산동 샘모루초교 주변지중화(총가) | 접속함설치, 관로굴착 더블캡, 미니크레인, 1t바가지, 5t덤프, 3w-1대 | 임재홍, 김성훈, 최정우, 김국진, 모범 1명 |  | 공사 일정 | N |  |  |  | admin | 2026-04-20T07:57:35.953900 | 2026-04-20 16:57:35
99 | 2026-04-22 |  | 광명동 광명3동복합청사 고압 800KW 신설(광덕SW10-1) |  |  |  | 공사 일정 | N |  |  |  | admin | 2026-04-03T09:04:38.393211 | 2026-04-03 18:04:38
169 | 2026-04-22 |  | 안양 개폐기 점검 |  | 이한열, 김기태 |  | 공사 일정 | Y | 2026-04-21T08:36:54.549435 | admin | 현황판 인라인 삭제 | admin | 2026-04-21T08:36:54.549458 | 2026-04-17 17:51:56
178 | 2026-04-22 |  | 고천동227-4 고천프라자 350kW 신설_3762 |  |  |  | 공사 일정 | Y | 2026-04-20T07:58:18.884726 | admin | 현황판 인라인 삭제 | admin | 2026-04-20T07:58:18.884747 | 2026-04-20 16:57:22
185 | 2026-04-22 |  | 비산동 샘모루초교 주변 지중화 (종가) | [팀] 공사2팀 접속함 설치, 관로굴착, 보도복구, 접속 (오륜전기) 2개소 3.5t 마이티, 1.2t 마이티, 더블캡, 2.5t 덤프, 3W - 1대 | 권TJ, 김CJ, 최TJ, 김GJ, 한GS, 모범2명, 오륜전기(2명) |  | 공사 일정 | Y | 2026-04-21T08:37:24.253035 | admin | 현황판 인라인 삭제 | admin | 2026-04-21T08:37:24.253059 | 2026-04-21 17:36:22
186 | 2026-04-22 |  | 자재 반입, 현장 조사, 자재 구매 | [팀] 공사3팀 자재 반입, 현장 조사, 자재 구매 1t 크레인, 1t 바가지 (구) | 최SJ, 견습 1명 |  | 공사 일정 | Y | 2026-04-21T08:39:17.879009 | admin | 현황판 인라인 삭제 | admin | 2026-04-21T08:39:17.879030 | 2026-04-21 17:36:22
187 | 2026-04-22 |  | 변압기 입고 (창고 이사) | [팀] 기타 3Φ 150kVA (N) x 2대 (지게차비: 010-8934-7501) | - |  | 공사 일정 | Y | 2026-04-21T08:40:45.441734 | admin | 현황판 인라인 삭제 | admin | 2026-04-21T08:40:45.441754 | 2026-04-21 17:36:22
184 | 2026-04-22 |  | 26년도 지상개폐기 점검 (안양지사) | 안양지사 - 1건 1t | 이한열, 김기태 |  | 공사 일정 | N |  |  |  | admin | 2026-04-21T08:36:49.192099 | 2026-04-21 17:36:49
151 | 2026-04-22 |  | 비산동 샘모루초교 주변 지중화 (총가) |  | 김성훈, 최정우, 김종인, 한동근, 모범 1명 |  | 공사 일정 | N |  |  |  | admin | 2026-04-21T08:37:20.512988 | 2026-04-21 17:37:20
135 | 2026-04-22 |  | 변압기 입고(창고 7시) | 3 150kva x 2대 지게차 : 010-8934-7501 |  |  | 일정 | N |  |  |  | admin | 2026-04-21T08:38:53.232613 | 2026-04-21 17:38:53
188 | 2026-04-22 |  | 현장조사 | 변산 1명 | 임재홍 |  | 일정 | N |  |  |  | admin | 2026-04-21T08:40:03.046555 | 2026-04-21 17:40:03
171 | 2026-04-22 |  | 자재여입 | 변산 1명 | 임재홍 |  | 일정 | N |  |  |  | admin | 2026-04-21T08:40:11.560902 | 2026-04-21 17:40:11
189 | 2026-04-22 |  | 자재구매 | 변산 1명 | 임재홍 |  | 일정 | N |  |  |  | admin | 2026-04-21T08:40:19.346726 | 2026-04-21 17:40:19
183 | 2026-04-23 |  | 안양 TR 동관단자 연결 |  |  |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-04-21T04:20:19.599059 | 2026-04-21 13:20:19
192 | 2026-04-23 |  | 고천동 227-4 고천프라자 장마W 신설 | [팀] 공사2팀 주간 도로컷팅: 20m x 2줄, 관로굴착: 약 3m (0.2, 0), 관로부설: (0.2, 0), 기초대 설치: T3-U x 1조 1번 크레인, 더블캡, 1번 미니 01, 5t 덤프, 6W-1대, 3W-1대, 15t 덤프-1대, 살수차 | 임SS, 최TJ, 김TJ, 김GJ, 한GS, 변산2명, 모법2명, <이재규> |  | 공사 일정 | Y | 2026-04-22T08:46:00.116297 | admin | 현황판 인라인 삭제 | admin | 2026-04-22T08:46:00.116320 | 2026-04-22 17:45:29
193 | 2026-04-23 |  | 비산동 샘모루초교 주변 지중화(총가) | [팀] 공사3팀 4/23~4/24 (야간) 케이블 풀링 CA 400, 케이블 풀링 CA 95 1번 크레인, 3번 크레인, 1t, 더블캡 | 김TJ, 김CJ, 김GJ, 김GS, 변산3명, 모법1명, <김우석> |  | 공사 일정 | Y | 2026-04-22T08:47:13.809560 | admin | 현황판 인라인 삭제 | admin | 2026-04-22T08:47:13.809583 | 2026-04-22 17:45:29
168 | 2026-04-23 |  | 고천동 227-4 고천프라자 신설 | 관로(0,2,0) 약 40m, T-3U 1조, TR 500KVA(N-1) 1대 TR935Q | 임재홍, 최정우, 김성훈, 김기태, 변산 2명, 모벙 2명 |  | 공사 일정 | N |  |  |  | admin | 2026-04-22T08:45:51.221154 | 2026-04-22 17:45:51
190 | 2026-04-23 |  | 26년 지상개폐기 점검 (안양지사 - 2팀) | 1t, 스카이(주) | 이한열, 김종인, 김기태, 변산1명, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-04-22T08:46:48.006919 | 2026-04-22 17:46:48
166 | 2026-04-23 |  | 안양 샘모루 초교 케이블 포설 |  | 김성훈, 김종인, 김국진, 김기태, 변산 3명, 모범 1명 |  | 공사 일정 | N |  |  |  | admin | 2026-04-23T08:17:53.294230 | 2026-04-23 17:17:53
191 | 2026-04-23 |  | 광명 삼천리 기기 점검 | [팀] 공사1팀 주간 개폐기 - 1개소 1t, 스카이(주) | 이한열, 김종인, 김기태, 변산 1명 |  | 공사 일정 | N |  |  |  | admin | 2026-04-23T08:38:27.174706 | 2026-04-23 17:38:27
167 | 2026-04-24 |  | 케이블 포설, TR 설치 |  | 임재홍, 이한열, 최정우, 한동근, 모범 1명 |  | 공사 일정 | Y | 2026-04-23T08:41:43.577728 | admin | 현황판 인라인 삭제 | admin | 2026-04-23T08:41:43.577750 | 2026-04-17 17:49:56
200 | 2026-04-24 |  | 안양 샘모루 초교 케이블 포설 |  |  |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-04-23T08:17:20.511340 | 2026-04-23 17:17:20
201 | 2026-04-24 |  | 호계동 1003-7 저압 J/B 분리 (08:00) | [팀] 공사1팀 호계동 1003-7 저압 S/B 분리 (08:00) 더블캡 | 최정우, 이한열, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-23T08:39:15.417841 | 2026-04-23 17:39:15
202 | 2026-04-24 |  | 고천동 207-4 교육청 64kW 신설 | [팀] 공사1팀 TR 수용가 압착 연결 CV 70 x 4L, TR 저압 압착 연결 - CV 70 x 4L 더블캡 | 최정우, 이한열, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-23T08:39:52.131427 | 2026-04-23 17:39:52
203 | 2026-04-24 |  | 고천동 227-4 고천 프라자 350kW 신설 | [팀] 공사2팀 케이블 철거 및 상부측 단말 절단, 케이블 풀링(CA95) = 100m x 3조, TR 설치 = 3Φ 500K x 1대, 접속(오전프라자) = 직선 95 x 2조, TR 95 x 2조 1t, 1번 크레인 | 임재홍, 이한열, 최정우, 한동근, 모범1명, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-23T08:40:49.001850 | 2026-04-23 17:40:48
204 | 2026-04-24 |  | 오전동 32-7 오전 4구역 3250kW 신설 | [팀] 공사3팀 도로 컷팅 (현장조사) 2줄 (약 30m) 1번 매니더, 1t | 임재홍, 이한열, 최정우, 한동근 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-23T08:41:31.026592 | 2026-04-23 17:41:31
170 | 2026-04-27 |  | 대농 m/h2 4UM 교체 |  |  |  | 공사 일정 | Y | 2026-04-24T09:08:05.063422 | admin | 현황판 인라인 삭제 | admin | 2026-04-24T09:08:05.063444 | 2026-04-17 17:52:22
180 | 2026-04-27 |  | 안양 샘모루초교 저압 입상, 전주신설 관로 구성 |  |  |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-04-20T08:01:28.105068 | 2026-04-20 17:01:28
182 | 2026-04-27 |  | 보상관련 지장물 조사 준비 |  |  |  | 일정 | N |  |  |  | 전자칠판 | 2026-04-20T22:49:27.477886 | 2026-04-21 07:49:27
205 | 2026-04-27 |  | 오전동 32-7 오전 나 구역 3,250k 신설 | 도로컷팅 관로굴착 기초대설치 | 최정우, 김성훈, 김기태, 변산 4명, 모범 2명, 이재규 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-04-24T09:08:01.202402 | 2026-04-24 18:08:01
206 | 2026-04-27 |  | 고천동 227-4 어반산업 115kw 신설 |  | 임재홍, 최정우, 김국진, 김기태, 변산 1명, 모범 1명, 이재규 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-04-26T23:32:36.361735 | 2026-04-27 08:32:36
211 | 2026-04-28 |  | 수암천 현장 집기류 전달 | 냉장고, 의자, 칠판 |  |  | 일정 | N |  |  |  | 전자칠판 | 2026-04-27T08:23:58.964705 | 2026-04-27 17:23:58
199 | 2026-04-28 |  | 오전동 32-7 오전 나구역 3250kw |  | 최정우, 김성훈, 김국진, 변산 4명, 모범 2명, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-27T08:25:27.052736 | 2026-04-27 17:25:27
209 | 2026-04-28 |  | 상동 580-1 의왕도시 공사 신설 | 기초대 설치 : 3W x 1조 관로 굴착 : 약 8m 케이블 재사 풀링 | 임재홍, 최정우, 김성훈, 김기태, 변산 2명, 모범 1명, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-27T08:25:37.778844 | 2026-04-27 17:25:37
210 | 2026-04-28 |  | 26년 지상 개폐기 점검 | 안양지사 | 이한열, 김종인, 김기태, 한동근, 김상훈 |  | 공사 일정 | N |  |  |  | admin | 2026-04-27T08:25:46.624087 | 2026-04-27 17:25:46
198 | 2026-04-29 |  | 개폐기 점검 |  |  |  | 공사 일정 | Y | 2026-04-28T08:46:42.727405 | admin | 현황판 인라인 삭제 | admin | 2026-04-28T08:46:42.727427 | 2026-04-23 17:15:54
197 | 2026-04-29 |  | 삼천리 수용가 엘보 접속 |  | 임재홍, 이한열 |  | 공사 일정 | Y | 2026-04-28T08:46:38.566468 | admin | 현황판 인라인 삭제 | admin | 2026-04-28T08:46:38.566491 | 2026-04-27 08:33:02
208 | 2026-04-29 |  | 1층 주차장 청소 및 정리, 공구 배치 |  | 임재홍, 한동근 |  | 일정 | N |  |  |  | admin | 2026-04-28T08:22:26.151916 | 2026-04-28 17:22:26
207 | 2026-04-29 |  | 오전동 오전 나구역 접속 | 케이블 풀링: CA400 x 약 120m x 3D 기기 설치, 접속(오륜전기) | 최정우, 이한열, 김국진, 변산 2명, 모범 1명, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-28T08:44:18.395751 | 2026-04-28 17:44:18
179 | 2026-04-29 |  | 초평동 한국 토지 공사 지장 전주 이설(총가) | 관로굴착, 접속함 설치, 저압풀링 및 접속, 저압 입상 | 이한열, 김종인, 김기태, 변산 2명, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-04-28T08:45:16.457122 | 2026-04-28 17:45:16
212 | 2026-04-29 |  | 자재 수령 (정우자재) -15시 | 시흥 업체 수령 | 임재홍, 한동근 |  | 일정 | N |  |  |  | 전자칠판 | 2026-04-28T08:46:25.573051 | 2026-04-28 17:46:25
196 | 2026-04-29 |  | 안양 샘모루 초교 맨홀 정리 |  | 김성훈, 김종인, 김기태, 모범1명 |  | 공사 일정 | N |  |  |  | admin | 2026-04-28T08:47:17.630614 | 2026-04-28 17:47:17
213 | 2026-04-29 |  | 안양 저압단가 |  |  |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-04-28T08:48:10.157453 | 2026-04-28 17:48:10
181 | 2026-04-30 |  | 대화감정 보상관련 지장물 조사 |  |  |  | 일정 | N |  |  |  | 김명호 | 2026-04-20T22:48:27.887560 | 2026-04-21 07:48:27
195 | 2026-04-30 |  | 상동 의왕 도시 공사 | -관로(0,2,0) 약 9m, TR95Sq 약 30m 1회선 신설 | 임재홍, 최정우, 김성훈, 김국진, 변산 2, 모범 1,이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-29T05:09:34.588241 | 2026-04-29 14:09:34
214 | 2026-04-30 |  | 삼천리 수용가 엘보 접속 |  | 임재홍, 한동근, 김무선 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-04-29T05:10:05.339067 | 2026-04-29 14:10:05
194 | 2026-04-30 |  | 안양 샘모루 초교 접속 |  | 오륜전기, 모범 1, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-04-29T05:10:27.666490 | 2026-04-29 14:10:27
215 | 2026-05-02 |  | 수용가 엘보 재접속(오륜전기) | 범계 sw38 | 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-29T05:11:08.850773 | 2026-04-29 14:11:08
216 | 2026-05-04 |  | 안양초 지중화 민원 구간(맨홀) 도로커팅 | 뚜껑 센터 기준 1.5m | 김도윤 |  | 공사 일정 | N |  |  |  | admin | 2026-04-30T05:31:30.273641 | 2026-04-30 14:31:30
217 | 2026-05-04 |  | 저압단가 |  | 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-04-30T05:31:37.056480 | 2026-04-30 14:31:37
218 | 2026-05-04 |  | 개폐기 점검 |  | 김상훈 |  | 공사 일정 | N |  |  |  | admin | 2026-04-30T05:31:45.374838 | 2026-04-30 14:31:45
219 | 2026-05-06 |  | 비산동 샘모루 초교 주변 지중화(총가) | 케이블 풀링(CA95) - 2구간 고압입상 : CA95x1조 (편출) 접속(영전사) : 종단95x1조 장주: 3개소(정장주) | 임재홍, 이한열, 최정우, 김종인, 김성훈, 김국진, 김기태, 한동근 |  | 공사 일정 | N |  |  |  | admin | 2026-05-05T23:40:50.042977 | 2026-05-06 08:40:50
220 | 2026-05-07 |  | 삼양 변전소 PD 불량 직선 접속재 보수 |  | 임재홍, 오륜전기 |  | 공사 일정 | Y | 2026-05-06T08:15:22.158221 | admin | 현황판 인라인 삭제 | admin | 2026-05-06T08:15:22.158241 | 2026-04-30 14:26:18
222 | 2026-05-07 |  | 삼천리 수용가 엘보연결(오후) |  |  |  | 공사 일정 | Y | 2026-05-06T08:15:10.822284 | admin | 현황판 인라인 삭제 | admin | 2026-05-06T08:15:10.822306 | 2026-04-30 14:26:50
234 | 2026-05-07 |  | 군포로 JB 민원처리(보수) |  | 최정우, 한동근 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-05T23:37:28.644851 | 2026-05-06 08:37:28
236 | 2026-05-07 |  | 파영관 175 x 540m 07시 입고 |  |  |  | 일정 | N |  |  |  | admin | 2026-05-05T23:38:23.662745 | 2026-05-06 08:38:23
243 | 2026-05-07 |  | 부림 s/w5 외 수명 만료 노후 지중 케이블 교체 공사 | 맨홀 양수 및 방수구 제거 사전 조사 야간 작업 준비 | 김성훈, 김종인, 김기태, 김상훈 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-06T08:12:13.675286 | 2026-05-06 17:12:13
239 | 2026-05-07 |  | 저압 단가 2건 | 의왕 고천(Bssx4). 의왕학의<동관 35x4) | 최정우, 한동근, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-05-06T08:13:12.703866 | 2026-05-06 17:13:12
235 | 2026-05-07 |  | 자재여입 | 김GJ 오후 3시 <착공안전회의> 김상훈 => 안양지사 | 이한열, 김국진 |  | 일정 | N |  |  |  | admin | 2026-05-06T08:14:15.220260 | 2026-05-06 17:14:15
221 | 2026-05-07 |  | 안양초 지중화 | 맨홀 뚜껑 인상분 맨홀목 땜방 - 1개소 | 최정우, 한동근, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-05-06T08:14:57.630741 | 2026-05-06 17:14:57
244 | 2026-05-07 |  | 접속제 바라시 | 데드 60 x 2조, 데드 95 x 2조 TR 95 x 1조 | 이한열, 김국진 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-06T08:16:06.898172 | 2026-05-06 17:16:06
245 | 2026-05-07 |  | 화성 남양 뉴타운 배전간선 | -남양 s/s 전력구 접속점 보수(오륜전기) VLF 진단 | 임재홍, 오륜전기 2명, 김무선 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-06T08:28:24.954126 | 2026-05-06 17:28:24
246 | 2026-05-07 |  | 일직동 511-2 전기공급(삼천리) | 삼천리 s/w 022H1-2 : 수용가 엘보연결 | 임재홍, 오륜전기 2명, 김무선 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-06T08:29:17.081842 | 2026-05-06 17:29:17
248 | 2026-05-07 |  | 군포중 주변 지중화 | 케이블 풀링(CA400) | 김성훈, 이한열, 김종인, 김국진, 김기태, 모범 1명, 김무선 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-06T08:30:36.361684 | 2026-05-06 17:30:36
247 | 2026-05-07 |  | 비산동 샘모루 초교 주변 지중화 | -케이블 풀링(CA400) | 김성훈, 이한열, 김종인, 김국진, 김기태, 모범 1명, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-05-06T08:30:47.329438 | 2026-05-06 17:30:47
223 | 2026-05-08 |  | 호계동 533-1 신설 | TR 325 SQ 약 280m 1회선 신설 |  |  | 공사 일정 | Y | 2026-05-05T23:44:52.768461 | admin | 현황판 인라인 삭제 | admin | 2026-05-05T23:44:52.768482 | 2026-04-30 14:27:43
225 | 2026-05-08 |  | 안양 샘모루 초교 |  |  |  | 공사 일정 | Y | 2026-05-05T23:44:45.376450 | admin | 현황판 인라인 삭제 | admin | 2026-05-05T23:44:45.376471 | 2026-04-30 14:28:29
237 | 2026-05-08 |  | 고천동 현대산업개발(주) 임시 | -접속(영전사):데드 60x1조(시공 목표 : 560,000) | 임재홍, 최정우, 한동근, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-05-07T08:01:20.609000 | 2026-05-07 17:01:20
238 | 2026-05-08 |  | 삼동580-1 의왕 도시공사 신설 접속 | -접속(영전사): 데드 50x1조, 데드95x2조 TR 95x1조(시공 목표 : 1.600,000) | 임재홍, 최정우, 한동근, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-05-07T08:02:39.946252 | 2026-05-07 17:02:39
251 | 2026-05-08 |  | 고천동 227-4 어반산업 개발 신설 | -J/B 내 접속(BLx4 연결) | 임재홍, 최정우, 한동근, 이재규 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-07T08:03:33.100782 | 2026-05-07 17:03:33
252 | 2026-05-08 |  | 조작 안전회의 참석(안양지사 14:30) |  | 한동근, 김상훈 |  | 일정 | N |  |  |  | admin | 2026-05-07T08:04:14.745114 | 2026-05-07 17:04:14
253 | 2026-05-08 |  | 케이블 입고(창고 07시) | CA400 : 400m x 3D (화물기사 : 010-8820-4960) 지게차비 : 010 - 9141 - 9214 |  |  | 일정 | N |  |  |  | 전자칠판 | 2026-05-07T08:05:06.730381 | 2026-05-07 17:05:06
228 | 2026-05-11 |  | 안양 케이블 교체 |  |  |  | 공사 일정 | Y | 2026-05-08T08:48:03.255984 | admin | 현황판 인라인 삭제 | admin | 2026-05-08T08:48:03.255984 | 2026-04-30 14:29:24
254 | 2026-05-11 |  | 고천동 현대 산업 임시 엘보변경 | -수용가 엘보연결 (고텍 s/w 30 # 2) | 최정우, 김국진, 김도윤 |  | 공사 일정 | N |  |  |  | admin | 2026-05-08T08:45:43.470124 | 2026-05-08 17:45:43
257 | 2026-05-11 |  | 고천동 227-4 어반산업 | 시공 목표 : 500000 | 최정우, 김국진, 김도윤 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-08T08:46:32.316408 | 2026-05-08 17:46:32
240 | 2026-05-11 |  | 부림 s/w5 외 수명 만료 노후 지중 케이블 교체 공사 | 범계 s/w 73 #3 ~ 범계 s/w 95 #3 -> 약 300m 시공 목표 : 15,000,000 | 임재홍, 최정우, 이한열, 김종인, 김국진, 김기태, 모범 1명, 김상훈 |  | 공사 일정 | N |  |  |  | admin | 2026-05-08T08:46:50.209720 | 2026-05-08 17:46:50
258 | 2026-05-11 |  | 산본 TR 41(영전사 미시공건) | - 저압 연결(동관 50x 4 입착, 활선연결) - NDIS 사진 촬영 | 이한열, 한동근 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-08T08:47:57.459995 | 2026-05-08 17:47:57
259 | 2026-05-11 |  | 현장 주말 돌발 대기(5/9 ~ 5/10) |  | 임재홍, 김국진 |  | 일정 | N |  |  |  | admin | 2026-05-11T08:14:09.537276 | 2026-05-11 17:14:09
226 | 2026-05-12 |  | 삼성 s/w 20 돌발소산 지상개폐기 교체공사 | 삼성 s/w 20 기기교체, 삼성 m/m 20 ~ 삼성 s/w 20 # 3 -> 약 40m | 김상훈 |  | 공사 일정 | Y | 2026-05-11T08:16:01.121781 | admin | 현황판 인라인 삭제 | admin | 2026-05-11T08:16:01.121781 | 2026-05-06 08:49:23
229 | 2026-05-12 |  | 부림 s/w5 외 수명 만료 노후 지중 케이블 교체 공사 | -접속(오륜전기) -직선 95 x 1조, 데스95 x 2조 | 오륜전기 2명, 모범 1명, 김상훈 |  | 공사 일정 | N |  |  |  | admin | 2026-05-11T08:13:54.079851 | 2026-05-11 17:13:54
241 | 2026-05-12 |  | 비산 샘모루 초교 주변 지중화(총가) | 관로굴착(보도 통신 병행) - 2개소 - 보도 약 20m(0,1,0) - 보도 약 35m(0,0,1) 시공 목표 금액 : 3569920 | 김성훈, 이한열, 김종인, 김국진, 김기태, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-05-11T08:15:48.885790 | 2026-05-11 17:15:48
262 | 2026-05-12 |  | 안양 접속함 주변 민원 처리 |  | 이재규 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-11T08:19:16.553593 | 2026-05-11 17:19:16
263 | 2026-05-12 |  | 우인찌 용접수리 |  | 임재홍, 김도윤 |  | 일정 | N |  |  |  | 전자칠판 | 2026-05-11T08:19:34.863039 | 2026-05-11 17:19:34
264 | 2026-05-12 |  | 부곡동 가스 트론 신설 | 수용가 엘보 연결 및 개폐기 투입 첨단 s/w 115 # 2 | 임재홍, 김도윤 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-11T08:20:13.721432 | 2026-05-11 17:20:13
261 | 2026-05-12 |  | 내손 라구역 대우건설 160kw | 케이블 풀링(CA95): 약 40m x 3D (2라인) 변압기 설치 : 300kva(n1) x 1대 시공 목표 금액 : 3,000,000 | 최정우, 이한열, 김성훈, 김종인, 김국진, 김기태, 한동근, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-05-11T08:20:39.509982 | 2026-05-11 17:20:39
260 | 2026-05-12 |  | 내손 라구역GS건설 300kw | -케이블 풀링(CA95) : 약 150m x 3D(2라인) 시공 목표 금액 : 8,400,000 | 최정우, 이한열, 김성훈, 김종인, 김국진, 김기태, 한동근, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-05-11T08:20:42.738995 | 2026-05-11 17:20:42
230 | 2026-05-13 |  | 안양 케이블 교체 |  |  |  | 공사 일정 | Y | 2026-05-05T23:49:52.104654 | admin | 현황판 인라인 삭제 | admin | 2026-05-05T23:49:52.104677 | 2026-04-30 14:29:39
233 | 2026-05-13 |  | 부림 s/w5 외 수명 만료 노후 지중 케이블 교체 공사 | -구간: 부림 s/w 21 # 2 ~ 부림 s/w 22 # 3 : 7m(cn60 -> ca95) -접속(오륜전기) : 데드95 x 2조 -구간: 부림 s/w 29 # 4 ~ 부림 s/w 30 # 1 : 8m(cn60->ca95) -접속(오륜전기) : 데드95 x 2조 시공 목표 금액 : 2,350,000 | 임재홍, 최정우, 한동근, 오륜전기 2명, 김상훈 |  | 공사 일정 | N |  |  |  | admin | 2026-05-12T23:42:41.396063 | 2026-05-13 08:42:41
227 | 2026-05-13 |  | 군포중 지중화(접속) | -고압접속(오륜전기) -직선 x 4조 시공 목표 금액 : 3,550,000 | 오륜전기 2명, 모범 1명, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-05-12T23:43:08.070695 | 2026-05-13 08:43:08
250 | 2026-05-14 |  | NDIS 사진 촬영 2건 + 현장조사 |  | 임재홍, 이한열, 최정우, 김성훈, 김종인, 한동근 |  | 일정 | N |  |  |  | admin | 2026-05-07T23:42:10.426164 | 2026-05-08 08:42:10
242 | 2026-05-14 |  | 군포중 지중화(접속) | -접속(오륜전기) | 오륜전기 2명, 모범 1명, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-05-13T08:14:03.358016 | 2026-05-13 17:14:03
265 | 2026-05-14 |  | 케이블 입고(07시 창고) | 내손 라구역 GS건설 신설 CA95 : 500m x 6드럼 지게차 : 010 - 4492 - 9030 |  |  | 일정 | N |  |  |  | 전자칠판 | 2026-05-13T08:14:49.014581 | 2026-05-13 17:14:49
231 | 2026-05-14 |  | 호계동 533-1 평촌 이반벨리 신설 | TR 325sq 약 280m 1회선 신설 | 최정우, 이한열, 김성훈, 김종인, 김국진, 한동근, 모범 2명, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-05-13T08:15:16.089932 | 2026-05-13 17:15:16
232 | 2026-05-15 |  | 안양 케이블 교체 |  |  |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-04-30T05:29:52.086685 | 2026-04-30 14:29:52
255 | 2026-05-15 |  | 26년 개폐기 점검 14시 |  | 임재홍, 김기태 |  | 공사 일정 | N |  |  |  | admin | 2026-05-13T23:37:38.452374 | 2026-05-14 08:37:38
267 | 2026-05-15 |  | 내손 라구역 주택동 150k 잠정 | 케이블 철거 : CA95 x 약 20m x 3D 입상 금구류 철거 | 임재홍, 김기태 |  | 공사 일정 | N |  |  |  | admin | 2026-05-14T08:11:03.813994 | 2026-05-14 17:11:03
266 | 2026-05-15 |  | 호계동 533-1 평촌 어반 관로굴착 09:00 | -관로굴착 : 약 20m(0,1,0) s/w~입상 가공 전주 활입 장비 지원 요청 | 임재홍, 김기태 |  | 공사 일정 | N |  |  |  | admin | 2026-05-14T08:11:26.038192 | 2026-05-14 17:11:26
249 | 2026-05-18 |  | 호계동 533-1 평촌 어반 밸리 신설 | -케이블 풀링 : CA95 x 17M x 3D -고압 입상 : CA95 x 1조 -접속(영전사) : 데드 95 x 1조 신설 s/w #3 연결 | 이한열, 최정우, 한동근, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-05-15T09:21:08.199450 | 2026-05-15 18:21:08
268 | 2026-05-18 |  | CA95 x 500m -> 3등분 드럼감기 |  | 임재홍, 김성훈, 김종인, 김국진, 김기태 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-15T09:21:56.278045 | 2026-05-15 18:21:56
269 | 2026-05-18 |  | CE325x429m -> 2등분 드럼감기 |  | 임재홍, 김성훈, 김종인, 김국진, 김기태 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-15T09:22:17.952045 | 2026-05-15 18:22:17
270 | 2026-05-18 |  | 야적장 파렛트 반출처리 | -화성 양감면 업체 전달 | 임재홍, 김성훈, 김종인, 김국진, 김기태 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-15T09:22:35.476285 | 2026-05-15 18:22:35
271 | 2026-05-18 |  | 절연캡(개폐기) 세척 |  |  |  | 일정 | N |  |  |  | 전자칠판 | 2026-05-15T09:22:47.850052 | 2026-05-15 18:22:47
272 | 2026-05-18 |  | 삼동 580-1 의왕 도시공사 신설 | -복구절체(오전 10:00) -수용가 엘보 연결 | 김성훈, 김상훈 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-15T09:23:26.273831 | 2026-05-15 18:23:26
224 | 2026-05-19 |  | 안양동 682-3 현대건설 지중외상 고장 복구 공사(굴착) |  |  |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-04-30T05:28:08.825204 | 2026-04-30 14:28:08
273 | 2026-05-19 |  | 안양 저압 단가 |  |  |  | 공사 일정 | N |  |  |  | admin | 2026-05-17T23:43:33.239037 | 2026-05-18 08:43:33
274 | 2026-05-19 |  | 군포중 지중화 직선접속 |  |  |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-17T23:43:46.552135 | 2026-05-18 08:43:46
256 | 2026-05-20 |  | CE325SQx3Dx약 180m 케이블 철거 신설 |  |  |  | 공사 일정 | Y | 2026-05-19T09:03:15.105816 | admin | 현황판 인라인 삭제 | admin | 2026-05-19T09:03:15.105816 | 2026-05-08 08:41:28
275 | 2026-05-20 |  | 광명역 역세권 지구 저압 접속함 점검 |  |  |  | 공사 일정 | Y | 2026-05-19T09:03:12.733339 | admin | 현황판 인라인 삭제 | admin | 2026-05-19T09:03:12.733339 | 2026-05-18 08:44:05
286 | 2026-05-20 |  | 우천예정 정비 | -개폐기 절연캡 세척 -엔진오일 교환 -구조삼각대 및 산소통 교육 -그외 장비 정비 | 임재홍, 이한열, 김성훈, 김종인, 김국진, 김기태, 한동근 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-19T09:04:05.032220 | 2026-05-19 18:04:05
287 | 2026-05-20 |  | 신규 공사건 현장 협의 |  | 임재홍, 이재규 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-19T09:04:16.889448 | 2026-05-19 18:04:16
276 | 2026-05-21 |  | 26년 상반기 훈련 |  |  |  | 공사 일정 | Y | 2026-05-20T08:06:52.929375 | admin | 현황판 인라인 삭제 | admin | 2026-05-20T08:06:52.929375 | 2026-05-18 08:44:32
277 | 2026-05-21 |  | 노후케이블 교체 |  |  |  | 공사 일정 | Y | 2026-05-20T08:06:51.105280 | admin | 현황판 인라인 삭제 | admin | 2026-05-20T08:06:51.105280 | 2026-05-18 08:45:21
278 | 2026-05-21 |  | 안양동 682-3 현대건설 지중외상 복구공사 |  |  |  | 공사 일정 | Y | 2026-05-20T08:06:48.345374 | admin | 현황판 인라인 삭제 | admin | 2026-05-20T08:06:48.345374 | 2026-05-18 08:45:37
279 | 2026-05-21 |  | 군포중 지중화 직선접속 |  | 오륜전기 2명, 모범 1명, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-05-20T08:06:26.583149 | 2026-05-20 17:06:26
289 | 2026-05-21 |  | 고,저압 드럼 정리 |  | 최정우, 김기태, 한동근 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-20T08:07:09.801736 | 2026-05-20 17:07:09
290 | 2026-05-21 |  | 삼천리 접속함 점검 및 신용인 s/s 회의 |  | 임재홍, 김종인, 김무선 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-20T08:07:42.810252 | 2026-05-20 17:07:42
288 | 2026-05-21 |  | 자재수령 |  | 이한열, 김성훈, 김국진 |  | 공사 일정 | N |  |  |  | admin | 2026-05-20T08:07:54.920225 | 2026-05-20 17:07:54
291 | 2026-05-21 |  | 개폐기 인계 및 인수(안산 장상동) | -44da | 김종인, 김기태 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-20T08:08:26.791778 | 2026-05-20 17:08:26
292 | 2026-05-21 |  | 밀폐공간 구로 삼각대 안전교육 및 시연회 |  | 김성훈, 이한열, 김종인, 김국진, 김기태 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-20T08:08:54.998877 | 2026-05-20 17:08:54
293 | 2026-05-21 |  | 하얀지구 h314 노후케이블 교체 | -맨홀 양수 및 방수구 철거 - 3개소 -맨홀 뚜껑 땅에 묻힘 찾아야함 |  |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-20T08:09:40.421980 | 2026-05-20 17:09:40
280 | 2026-05-22 |  | 하얀지구 노후 케이블 교체 |  |  |  | 공사 일정 | Y | 2026-05-21T07:54:45.992214 | admin | 현황판 인라인 삭제 | admin | 2026-05-21T07:54:45.992214 | 2026-05-18 08:46:03
294 | 2026-05-22 |  | 학의동 1181 리젠시빌 신설 | -기초대 설치 : 3w x 1조 -관로 굴착 : 약 3개(3, 0, 0) -케이블 풀링(CA95) -기기설치 | 임재홍, 최정우, 이한열, 김성훈, 김국진, 김기태, 변산 1명, 이재규 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-21T07:56:10.558685 | 2026-05-21 16:56:10
281 | 2026-05-22 |  | 광명 역세권 지구 저압접속함 점검 |  | 김종인, 한동근, 변산 2명, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-05-27T08:37:57.381923 | 2026-05-27 17:37:57
282 | 2026-05-26 |  | 광명 하안지구 H314 노후 케이블 교체 |  |  |  | 공사 일정 | Y | 2026-05-22T04:30:22.489296 | admin | 현황판 인라인 삭제 | admin | 2026-05-22T04:30:22.489296 | 2026-05-19 09:29:27
285 | 2026-05-26 |  | 군포중 직선접속 |  |  |  | 공사 일정 | Y | 2026-05-25T23:35:28.828727 | admin | 현황판 인라인 삭제 | admin | 2026-05-25T23:35:28.828727 | 2026-05-19 09:30:47
295 | 2026-05-26 |  | 26년 특정 재원 지상 개폐기 교체 | 소하 s/w 156 소하 s/w 90 | 임재홍, 최정우, 김성훈, 김국진 |  | 공사 일정 | N |  |  |  | admin | 2026-05-25T23:34:53.705618 | 2026-05-26 08:34:53
284 | 2026-05-26 |  | 광명 역세권 접속함 점검(삼천리) |  | 이한열, 김종인, 김기태, 한동근 |  | 공사 일정 | N |  |  |  | admin | 2026-05-27T08:36:09.951390 | 2026-05-27 17:36:09
301 | 2026-05-27 |  | 광명동 광명시장 일반동 신설 | - 기초대 설치 : 3w x 1조 - 관로굴착 - 시공 목표금액 : 4,007,000 | 최정우, 김성훈, 한동근, 모범 1명, 이재규 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-26T08:50:22.394415 | 2026-05-26 17:50:22
302 | 2026-05-27 |  | NDIS 사진 촬영 | 완료 후 접속함 점검 합류 | 임재홍, 이한열, 김국진 |  | 공사 일정 | N |  |  |  | 전자칠판 | 2026-05-26T08:50:48.003444 | 2026-05-26 17:50:48
304 | 2026-05-27 |  | 케이블 입고(07시 창고) | ca95: 500m x 3D | 이한열 |  | 일정 | N |  |  |  | 전자칠판 | 2026-05-26T08:51:34.755290 | 2026-05-26 17:51:34
305 | 2026-05-27 |  | 만안 s/w 40, 삼덕 M/u 외상고장 |  | 김종인 |  | 일정 | N |  |  |  | 전자칠판 | 2026-05-26T08:51:58.811177 | 2026-05-26 17:51:58
306 | 2026-05-27 |  | 광명동 광명시장 일반용신설 | 관로굴착 기기설치 시공 목표 금액 : 4,500,000 | 최정우, 김성훈, 한동근, 변산 3명, 모범 2명, 이재규 |  | 공사 일정 | N |  |  |  | admin | 2026-05-26T08:53:15.464707 | 2026-05-26 17:53:15
296 | 2026-05-27 |  | 광명 역세권 지구 저압 접속함 점검 |  | 김종인, 김기태, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-05-27T08:36:05.487174 | 2026-05-27 17:36:05
303 | 2026-05-27 |  | 군포중 주변 지중화 | 개폐기 접속 | 오륜전기 2명, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-05-27T08:37:38.898302 | 2026-05-27 17:37:38
300 | 2026-05-28 |  | 호계동 평촌 어반밸리 수용가 가압 |  |  |  | 공사 일정 | Y | 2026-05-27T08:37:31.151389 | admin | 현황판 인라인 삭제 | admin | 2026-05-27T08:37:31.151389 | 2026-05-22 13:31:25
297 | 2026-05-28 |  | 광명 역세권 지구 저압 접속함 점검 |  | 이한열, 김국진 |  | 공사 일정 | N |  |  |  | admin | 2026-05-27T08:35:59.009406 | 2026-05-27 17:35:59
299 | 2026-05-28 |  | 군포중 주변 지중화 | 저압 케이블 풀링 | 임재홍, 김종인, 김기태, 변산 3명, 모범 1명, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-05-27T08:36:51.321209 | 2026-05-27 17:36:51
283 | 2026-05-28 |  | 단가 장비, 인원 점검(16시) |  | 이한열, 김국진 |  | 일정 | N |  |  |  | admin | 2026-05-27T08:37:25.432052 | 2026-05-27 17:37:25
298 | 2026-05-29 |  | 광명 역세권 지구 저압 접속함 점검 |  | 이한열, 한동근, 변산 2명 |  | 공사 일정 | N |  |  |  | admin | 2026-05-28T09:34:50.887563 | 2026-05-28 18:34:50
307 | 2026-05-29 |  | 군포중 주변 지중화(총가) | -저압 케이블 풀링 | 임재홍, 김종인, 최정우, 김기태, 김국진, 김성훈, 모범 1명, 김무선 |  | 공사 일정 | N |  |  |  | admin | 2026-05-28T09:34:59.573268 | 2026-05-28 18:34:59
45 | 2099-12-31 | 테스트현장 | 테스트작업 |  |  |  | 공사 일정 | N |  |  |  | test | 2026-03-27T08:06:40.852145 | 2026-03-27 17:06:40

## 외출상태_스냅샷
user_name | status | location | until_time | note | updated_at | last_actor_user | last_actor_device | last_actor_at | exported_date
이재규 | 외출 | 호계동 | 2026-05-29T12:00 |  | 2026-05-29 09:18:47 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-29T00:18:47.890289 | 2026-05-29
김단후 | 외출 | 수암천(출근), 사무실(퇴근) |  |  | 2026-05-20 08:33:07 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/148.0.0.0 Safari/537.36 | 2026-05-19T23:33:07.770748 | 2026-05-29
김무선 | 사무실 |  |  |  | 2026-05-28 17:00:24 | auto-system | auto-system | 2026-05-28T08:00:24.852165 | 2026-05-29
김상훈 | 사무실 |  |  |  | 2026-05-28 14:00:19 | auto-system | auto-system | 2026-05-28T05:00:19.187414 | 2026-05-29
김도윤 | 사무실 |  |  |  | 2026-05-28 12:00:23 | auto-system | auto-system | 2026-05-28T03:00:23.992175 | 2026-05-29
고운선 | 사무실 |  |  |  | 2026-05-22 15:30:06 | auto-system | auto-system | 2026-05-22T06:30:06.024566 | 2026-05-29
조성현 | 사무실 | 비산동 | 2026-05-11T12:00 |  | 2026-05-11 11:51:31 | admin | Mozilla/5.0 (Windows NT 10.0; Win64; x64) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/147.0.0.0 Safari/537.36 | 2026-05-11T02:51:31.483922 | 2026-05-29
정재학 | 사무실 |  |  |  | 2026-04-08 14:42:04 | admin | Mozilla/5.0 (Linux; Android 10; K) AppleWebKit/537.36 (KHTML, like Gecko) Chrome/146.0.0.0 Mobile Safari/537.36 | 2026-04-08T05:42:04.432480 | 2026-05-29

## 운영지표
metric | value
active_schedule_count | 2
schedule_created_count | 0
outing_status_snapshot_count | 8
admin_request_count | 0
photo_upload_count | 0
audit_event_count | 0
login_session_count | 0
chat_count | 0
schedule_update_count | 0
schedule_delete_count | 0
target_date | 2026-05-29
daily_active_user_count | 0